## Executive Summary
Chronic Care Cascade Pilot — Cost Model Overview
Pilot purpose
Demonstrate that a trusted intermediary can reuse existing standards-based clinical data and infrastructure to produce a governed diabetes dataset for state public health surveillance and CMS-aligned digital quality measurement, while reducing duplicative reporting and making data quality transparent.
What one modeled pilot site includes |  |  | Key modeling boundaries
Primary participant | 1 state PHA |  | Included | Participant labor, vendor fees, ODCs, participant indirects, site evaluation support, 7.5% contingency
Provider participants | 10 FQHCs and 2 other outpatient healthcare organizations |  | Excluded | Pre-award charter development, NP/prime administration, independent evaluation, post-pilot operations
Technical diversity | 5 source-system/vendor configurations; 2 shared FQHC configurations |  | Infrastructure posture | Existing interfaces, platforms, matching, trust, de-identification, monitoring, and analytics are configured—not rebuilt
Intermediary structure | One of three models defined on the Scenario Definitions sheet |  | Optional add-ons | UDS+ interface; chronic-care referral analysis; new medication-dispensing connection
Core outputs | PHA diabetes surveillance product and CMS122 |  | Primary user | State PHA; other federal and quality uses are secondary to the site cost build
Operating window | 12-month funded pilot with 9 months of live exchange (6-month sensitivity) |  | Clinical scope | Diabetes, priced as narrow A1c-focused and broad longitudinal cascade variants
How to use this workbook
1 | Select the target scenario (intermediary model and dataset scope) on the "Scenario Definitions" sheet.
2 | Adjust cost-sensitive quantities and assumptions on the "Assumptions & Inputs" sheet.
Source basis: Chronic Pilot Overview; Draft Chronic Care Cascade Pilot Data Flow Architectures; Tech Brief: PHIG B4 Chronic Care Cascade Pilot; and the approved scope assumptions developed for this cost model.
Estimate maturity: provisional bottom-up model. Labor rates, unit hours, vendor fees, participant indirect rates, and benchmark citations require validation before use as a procurement or funding commitment.
Pro Forma Cost Summary
Selected Scenario | Estimating Case | Low | Base | High
2A | HIE/HDU with HCCN | 1492378.275 | 3094276.35 | 8028489.55
| Metric | Low | Base | High
| Sponsor-funded cost before contingency | 1433402.025 | 2911271.7 | 7123349.275
| Contingency | 58976.25 | 183004.65 | 905140.275
| Sponsor-funded cost including contingency | 1492378.275 | 3094276.35 | 8028489.55
| Unreimbursed in-kind cost | 0 | 0 | 0
| Total economic cost | 1492378.275 | 3094276.35 | 8028489.55
| One-time implementation and evaluation | 1141936.275 | 2320041.1 | 6429867.55
| Recurring pilot operations | 350442 | 774235.25 | 1598622
| Monthly pilot operating run rate | 58407 | 86026.1389 | 177624.6667
| Organization Group | Low | Base | High
| State PHA | 212139.9 | 375621.1 | 927010.2
| HIE/HDU Intermediary | 788159.4 | 1523946.9 | 3568234
| HCCN | 262464.225 | 578428.5 | 1484093.45
| Healthcare Organizations & FQHCs | 229614.75 | 616279.85 | 2049151.9
| Lifecycle Workstream | Low | Base | High
| Implementation management | 202089 | 303779 | 610476
| Governance, legal, privacy, and security | 150347.4 | 307886.7 | 1106709.25
| Data specification and mapping | 92238.075 | 191686.25 | 483784.3
| Configuration and integration | 379185.15 | 734896.25 | 1790295.9
| Testing and remediation | 149182.275 | 391268.4 | 1262982.1
| Onboarding and training | 45847.125 | 124268.5 | 372939
| Pilot operations and support | 350442 | 774235.25 | 1598622
| Evaluation, playbook, and closeout | 123047.25 | 266256 | 802681
Optional Components
Add-On ID | Component | Active? | Base Increment | Trigger
ADD-01 | UDS+ interface and support | No | 370000 | Included only when UDS+ is in charter and no adequate pathway exists
ADD-02 | Closed-loop chronic-care referral analysis | No | 135000 | Requires an operational referral platform and governance model
ADD-03 | New MedicationDispense connection | No | 420000 | Required only when broad scope needs dispensing data not already available
ADD-10 | Formal security authorization or penetration testing | No | 330000 | Required by PHA/intermediary security authority
Key Estimate Caveats
Planning estimate | This model is intended for comparison and planning, not as a vendor quote or procurement commitment.
Existing-platform reuse | Base scope assumes existing exchange, matching, trust, de-identification, monitoring, and analytics capabilities are configured rather than rebuilt.
Rates and indirects | Labor rates, vendor fees, and participant indirect rates remain provisional and require validation.
Excluded costs | NP/prime administration, independent evaluation, pre-award chartering, and post-pilot operations are excluded.
Add-on treatment | Ordinary scale variables are handled through inputs; only ADD-01, ADD-02, ADD-03, and ADD-10 remain separate optional components.

## Scenario Definitions
Scenario Definitions
Scenario convention: the letter identifies dataset scope (A = narrow A1c-focused; B = broad longitudinal cascade). The number identifies the intermediary operating model.
| Selected Scenario | 2A
Scenario ID | Intermediary Model | Provider Structure | Dataset Scope | Operations | Key Distinction | Low Total | Base Total | High Total
1A | HIE/HDU without HCCN | 10 FQHCs + 2 healthcare organizations connect without HCCN consolidation | Narrow A1c-focused | 9 months | Most source connections; no HCCN managed-services layer | 1229914.05 | 2587667.85 | 6714496.1
1B | HIE/HDU without HCCN | Same as 1A | Broad longitudinal diabetes cascade | 9 months | Adds broader data, mapping, analytics, and validation | 1285904.55 | 2702027.85 | 7013848.6
2A | HIE/HDU with HCCN | HCCN consolidates 10 FQHCs; 2 healthcare organizations connect directly | Narrow A1c-focused | 9 months | HCCN adds managed services and reduces production interfaces | 1492378.275 | 3094276.35 | 8028489.55
2B | HIE/HDU with HCCN | Same as 2A | Broad longitudinal diabetes cascade | 9 months | Broad scope plus two intermediary/aggregation layers | 1548368.775 | 3208636.35 | 8327842.05
3A | HCCN acting as intermediary | HCCN ingests 10 FQHCs and 2 healthcare organizations; no HIE/HDU | Narrow A1c-focused | 9 months | HCCN performs full intermediary, trust, and PHA delivery functions | 977031.375 | 2187904.45 | 5846278.05
3B | HCCN acting as intermediary | Same as 3A | Broad longitudinal diabetes cascade | 9 months | Broad scope delivered entirely through HCCN intermediary model | 1033021.875 | 2302264.45 | 6145630.55
Separately priced add-ons and sensitivities
These packages are excluded from the base scenario unless their trigger occurs.
Add-On ID | Item | Trigger | Applies To | Model Treatment | Key Cost Driver | Low Total | Base Total | High Total
ADD-01 | UDS+ interface | Charter includes UDS+ and no adequate existing pathway is available | Any scenario | Optional add-on | May require a new interface, mapping, authentication, and HRSA validation | 170000 | 370000 | 750000
ADD-02 | Closed-loop chronic-care referral analysis | Charter includes referral add-on and an existing referral platform/governance model is operational | Any scenario with existing referral infrastructure | Optional add-on | Marginal workflow, data, and evaluation configuration only | 60000 | 135000 | 320000
ADD-03 | New medication-dispensing connection | Broad scope requires dispensing data not already available | Broad-scope scenarios if existing data are unavailable | Optional add-on | New pharmacy/payer interface and data-use work | 175000 | 420000 | 950000
ADD-04 | Additional non-FQHC healthcare organization | Participant count exceeds two | Any scenario | Marginal unit | Onboarding, legal, validation, training, and support | 30000 | 65000 | 135000
ADD-05 | Additional FQHC | FQHC count exceeds ten | Any scenario | Marginal unit | Onboarding, legal, validation, training, and support | 14000 | 31000 | 65000
ADD-06 | Additional source-system configuration | More than five distinct configurations or a materially different tenant pattern | Any scenario | Marginal unit | Mapping, interface configuration, testing, and remediation | 60000 | 125000 | 260000
ADD-07 | Additional production interface | Interface topology exceeds scenario base | Any scenario | Marginal unit | Mapping, interface configuration, testing, and remediation | 50000 | 105000 | 220000
ADD-08 | Additional remediation cycle | Two base remediation cycles are insufficient | Any scenario | Marginal unit | Vendor, provider, intermediary, and project-management effort | 40000 | 95000 | 230000
ADD-09 | Six-month operations sensitivity | Schedule permits only six live months or sponsor chooses shorter evidence period | Any scenario | Schedule sensitivity | Reduces recurring support and evaluation evidence period | -240000 | -440000 | -740000
ADD-10 | Formal security authorization or penetration testing | PHA/intermediary requires ATO-equivalent approval, independent assessment, or new control documentation | Any scenario | Marginal unit |  | 130000 | 330000 | 800000
ADD-11 | New environment or software license | Existing environment capacity or licenses are insufficient | Any scenario | Marginal unit |  | 110000 | 260000 | 650000
ADD-12 | High-intensity technical assistance | Readiness validation identifies material participant capability gaps | Any scenario | Marginal unit |  | 45000 | 105000 | 240000

## Assumptions & Inputs
Model Assumptions and Inputs
Core modeling assumptions
Assumption | Status | Cost Effect | Treatment
Pre-award charter is complete and not funded | Fixed | Reduces funded planning scope | Exclusion
Implementation plan is funded and derived from the charter | Fixed | Adds Month 1 implementation-management effort | Included
Existing FHIR and HL7 v2 endpoints are functioning | Moderate confidence | Avoids greenfield source-interface builds | Base assumption + contingency risk
Architecture and interface documents need minor updates only | High confidence | Limits architecture/design labor | Fixed assumption
Normalization, matching, deduplication, cohort, de-identification, aggregation, trust, monitoring, and analytics capabilities already exist | Moderate confidence | Primary cost-reduction assumption | Base assumption + contingency risk
Existing PHA analytics tool is configured; no new dashboard platform | High confidence | Avoids platform procurement and development | Fixed assumption
PHA receives aggregate and de-identified line-level data | Fixed | Requires two configured output forms | Included
Intermediary executes CMS122; PHA validates results | Provisional | Avoids duplicate measure-engine implementation | Editable assumption
MedicationRequest is required; MedicationDispense only if already available | Fixed | Avoids new pharmacy/payer connection in base | Base scope / add-on if needed
Two remediation cycles are sufficient | Moderate confidence | Caps vendor and participant rework | Base input + per-cycle sensitivity
Participant direct costs and indirect costs are fully reimbursed | Fixed | Increases total to full participant economic cost | Included
NP/prime administration and post-pilot operations are excluded | Fixed | Keeps estimate site-focused and time-limited | Exclusion
Highest-impact unresolved or variable items
Item | Provisional Assumption | Risk if Different | Model Handling
Formal security authorization | No new ATO or penetration test | Material documentation, testing, and schedule increase | Contingency / optional sensitivity
Trust acceptance thresholds | Feasibility-oriented; critical errors resolved, known completeness gaps documented | Stricter thresholds add remediation cycles | Editable assumption
Existing environment availability | Existing test/UAT/production capacity is sufficient | New environments add cloud, deployment, and security costs | Contingency risk
HCCN ability to serve non-FQHC providers | Legally and technically feasible in Scenario 3 | Scenario 3 may need another intermediary or reduced scope | Scenario risk
Broad care-cascade data completeness | Enough existing data to test feasibility | May require added sources or produce limited findings | Contingency risk / limitation
Participant indirect rates | Organization-specific actual rates | Large effect on topline cost | Editable participant inputs in cost build-up
Cost Model Inputs
Blue font / yellow fill = editable provisional input
Input ID | Input | Low | Base | High | Unit | Cost Model Use
IN-01 | Funded pilot sites | 1 | 1 | 1 | sites | Direct formula input
IN-02 | FQHCs | 5 | 10 | 20 | organizations | Direct formula input
IN-03 | Other healthcare organizations | 1 | 2 | 5 | organizations | Direct formula input
IN-04 | All provider organizations | 6 | 12 | 25 | organizations | Derived total; direct formula input
IN-05 | Source configurations | 3 | 5 | 8 | configurations | Direct formula input
IN-06 | Shared FQHC configurations | 1 | 2 | 4 | configurations | Direct formula input
IN-07 | Production interfaces used by selected scenario | 3 | 3 | 5 | interfaces | Scenario lookup used by HIE/HDU interface-related WBS rows
IN-08 | HCCN consolidated export | 1 | 1 | 1 | interface | Direct formula input
IN-09 | PHA receiving interface | 1 | 1 | 1 | interface | Direct formula input
IN-10 | Primary DUAs/DSAs | 3 | 3 | 5 | agreements | Direct formula input
IN-11 | HCCN agreement plus member amendments | 6 | 11 | 21 | legal instruments | Direct formula input
IN-12 | Line-level and aggregate outputs | 2 | 2 | 3 | output types | Direct formula input
IN-13 | PHA surveillance outputs | 1 | 1 | 2 | outputs | Direct formula input
IN-14 | CMS122 measures | 1 | 1 | 2 | measures | Direct formula input
IN-15 | Selected clinical scope | 1 | 1 | 1 | scope | Direct formula input
IN-16 | Broad-scope increment trigger | 1 | 1 | 1 | binary trigger | Scenario applicability trigger
IN-17 | Funded pilot duration | 12 | 12 | 14 | months | Direct formula input
IN-18 | Live exchange period | 6 | 9 | 9 | months | Direct formula input
IN-19 | Operational/status reporting cycles | 9 | 12 | 18 | cycles | Direct formula input
IN-20 | Governance meeting cycles | 9 | 12 | 18 | cycles | Direct formula input
IN-21 | Evaluation cycles | 3 | 4 | 6 | cycles | Direct formula input
IN-22 | Integrated test/UAT cycles | 2 | 3 | 4 | cycles | Direct formula input
IN-23 | Remediation cycles | 1 | 2 | 4 | cycles | Direct formula input
IN-24 | Source configuration remediation units | 3 | 10 | 32 | configuration-cycles | Derived scaling input
IN-25 | FQHC configuration remediation units | 1 | 4 | 16 | configuration-cycles | Derived scaling input
IN-26 | Provider/source remediation units | 3 | 10 | 32 | configuration-cycles | Derived scaling input
IN-27 | Site training cohorts | 2 | 4 | 6 | cohorts | Direct formula input
IN-28 | HCCN/FQHC training cohorts | 1 | 2 | 4 | cohorts | Direct formula input
IN-29 | Support tickets | 20 | 60 | 150 | tickets | Direct formula input
IN-30 | Provider-month support units | 36 | 108 | 225 | organization-months | Derived scaling input
IN-31 | Provider evaluation units | 18 | 48 | 150 | organization-cycles | Derived scaling input
IN-32 | PHA receiving systems | 1 | 1 | 2 | systems | Direct formula input
IN-33 | In-person events | 1 | 2 | 4 | events | Direct formula input
IN-34 | Contingency percentage | 5% | 7.5% | 15% | percent | Direct formula input
IN-35 | Production interfaces — with HCCN | 3 | 3 | 5 | interfaces | Scenario-specific source for IN-07
IN-36 | Production interfaces — without HCCN | 3 | 5 | 8 | interfaces | Scenario-specific source for IN-07
IN-37 | Diabetes population | 50000 | 150000 | 250000 | unique patients | Capacity/evaluation input; no direct base-cost effect
IN-38 | Daily incremental records | 500 | 750 | 1000 | records/day | Capacity/cloud sensitivity; no direct base-cost effect
IN-39 | Shared tools/templates provided | 50% | 75% | 90% | percent | Contextual assumption already reflected in provisional unit hours
Provisional Fully Loaded Labor Rates — Replace with Actual Rates or Validated Benchmarks
Rate ID | Organization Group | Rate Tier | Rate Basis | Direct Rate | Fringe | Overhead/G&A | Fee | Fully Loaded Rate | Dollar Year | Confidence
RT-01 | State PHA | Executive | Provisional fully loaded participant cost | 97.4 | 30% | 18% | 0% | 150 | 2026 | Low
RT-02 | State PHA | PM | Provisional fully loaded participant cost | 77.92 | 30% | 18% | 0% | 120 | 2026 | Low
RT-03 | State PHA | SME | Provisional fully loaded participant cost | 81.17 | 30% | 18% | 0% | 125 | 2026 | Low
RT-04 | State PHA | Technical | Provisional fully loaded participant cost | 87.66 | 30% | 18% | 0% | 135 | 2026 | Low
RT-05 | State PHA | Analyst | Provisional fully loaded participant cost | 61.69 | 30% | 18% | 0% | 95 | 2026 | Low
RT-06 | State PHA | Legal/Security | Provisional fully loaded participant cost | 116.88 | 30% | 18% | 0% | 180 | 2026 | Low
RT-07 | State PHA | Operations | Provisional fully loaded participant cost | 55.19 | 30% | 18% | 0% | 85 | 2026 | Low
RT-08 | HIE/HDU Intermediary | Executive | Provisional fully loaded participant cost | 113.64 | 30% | 18% | 4% | 175 | 2026 | Low
RT-09 | HIE/HDU Intermediary | PM | Provisional fully loaded participant cost | 94.16 | 30% | 18% | 4% | 145 | 2026 | Low
RT-10 | HIE/HDU Intermediary | SME | Provisional fully loaded participant cost | 103.9 | 30% | 18% | 4% | 160 | 2026 | Low
RT-11 | HIE/HDU Intermediary | Technical | Provisional fully loaded participant cost | 107.14 | 30% | 18% | 4% | 165 | 2026 | Low
RT-12 | HIE/HDU Intermediary | Analyst | Provisional fully loaded participant cost | 77.92 | 30% | 18% | 4% | 120 | 2026 | Low
RT-13 | HIE/HDU Intermediary | Legal/Security | Provisional fully loaded participant cost | 136.36 | 30% | 18% | 4% | 210 | 2026 | Low
RT-14 | HIE/HDU Intermediary | Operations | Provisional fully loaded participant cost | 68.18 | 30% | 18% | 4% | 105 | 2026 | Low
RT-15 | HCCN | Executive | Provisional fully loaded participant cost | 100.65 | 30% | 18% | 4% | 155 | 2026 | Low
RT-16 | HCCN | PM | Provisional fully loaded participant cost | 81.17 | 30% | 18% | 4% | 125 | 2026 | Low
RT-17 | HCCN | SME | Provisional fully loaded participant cost | 87.66 | 30% | 18% | 4% | 135 | 2026 | Low
RT-18 | HCCN | Technical | Provisional fully loaded participant cost | 94.16 | 30% | 18% | 4% | 145 | 2026 | Low
RT-19 | HCCN | Analyst | Provisional fully loaded participant cost | 68.18 | 30% | 18% | 4% | 105 | 2026 | Low
RT-20 | HCCN | Legal/Security | Provisional fully loaded participant cost | 123.38 | 30% | 18% | 4% | 190 | 2026 | Low
RT-21 | HCCN | Operations | Provisional fully loaded participant cost | 58.44 | 30% | 18% | 4% | 90 | 2026 | Low
RT-22 | Healthcare Organizations & FQHCs | Executive | Provisional fully loaded participant cost | 94.16 | 30% | 18% | 0% | 145 | 2026 | Low
RT-23 | Healthcare Organizations & FQHCs | PM | Provisional fully loaded participant cost | 74.68 | 30% | 18% | 0% | 115 | 2026 | Low
RT-24 | Healthcare Organizations & FQHCs | SME | Provisional fully loaded participant cost | 81.17 | 30% | 18% | 0% | 125 | 2026 | Low
RT-25 | Healthcare Organizations & FQHCs | Technical | Provisional fully loaded participant cost | 84.42 | 30% | 18% | 0% | 130 | 2026 | Low
RT-26 | Healthcare Organizations & FQHCs | Analyst | Provisional fully loaded participant cost | 61.69 | 30% | 18% | 0% | 95 | 2026 | Low
RT-27 | Healthcare Organizations & FQHCs | Legal/Security | Provisional fully loaded participant cost | 116.88 | 30% | 18% | 0% | 180 | 2026 | Low
RT-28 | Healthcare Organizations & FQHCs | Operations | Provisional fully loaded participant cost | 55.19 | 30% | 18% | 0% | 85 | 2026 | Low
Organization Group | Indirect Rate | Basis | Confidence | Notes
State PHA | 25% | Applied to direct labor only | Low | Provisional; replace with approved rate
HIE/HDU Intermediary | 35% | Applied to direct labor only | Low | Provisional; replace with approved rate
HCCN | 30% | Applied to direct labor only | Low | Provisional; replace with approved rate
Healthcare Organizations & FQHCs | 25% | Applied to direct labor only | Low | Provisional; replace with approved rate

## Cost Build-Up (hidden)
Stage 3 Costable Activity Register
This sheet decomposes the controlling Work Breakdown into activities with distinct cost ownership, scaling logic, scenario applicability, labor mix, non-labor inputs, estimating method, assumptions, and risks.
WBS ID | Parent WBS ID | Organization Group | Lifecycle Workstream | Work Package | Costable Activity | Description | Output or Completion Condition | Accountable Organization | Performing Party | Supporting Parties | Cost-Bearing Party | Funded or In Kind | Scenario Applicability | Cost Model Treatment | Scaling Classification | Scaling Unit | Quantity Input ID | Formula Type | Lead Labor Category | Supporting Labor Categories | Participant Labor | Vendor Labor | Reviewer or Approver | Non-Labor Inputs | Estimating Method | Benchmark ID | Complexity Level | Assumption IDs | Risk IDs | Include in Selected Scenario | Low Quantity | Base Quantity | High Quantity | Low Fixed Hours | Base Fixed Hours | High Fixed Hours | Low Hours per Unit | Base Hours per Unit | High Hours per Unit | Low Total Hours | Base Total Hours | High Total Hours | Rate ID | Loaded Rate | Low Labor Cost | Base Labor Cost | High Labor Cost | Low Non-Labor Cost | Base Non-Labor Cost | High Non-Labor Cost | Indirect Rate | Low Indirect Cost | Base Indirect Cost | High Indirect Cost | Contingency Eligible | Low Contingency | Base Contingency | High Contingency | Low Total Cost | Base Total Cost | High Total Cost | BOE Status | Validation Status | Source ID | Adjustment / Notes | Include 1A | Include 1B | Include 2A | Include 2B | Include 3A | Include 3B | 1A Low Total | 1A Base Total | 1A High Total | 1B Low Total | 1B Base Total | 1B High Total | 2A Low Total | 2A Base Total | 2A High Total | 2B Low Total | 2B Base Total | 2B High Total | 3A Low Total | 3A Base Total | 3A High Total | 3B Low Total | 3B Base Total | 3B High Total
WBS-01.01.01 | WBS-01.01 | State PHA | Implementation management | Implementation planning | Develop funded implementation plan | Translate the approved pre-award charter into workstreams, activities, owners, milestones, dependencies, and acceptance gates. | Approved implementation plan with traceability to charter decisions | PHA | PHA project team | Intermediary; HCCN; providers | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per site | pilot site | IN-01 | Fixed hours | Project manager | Program director; business analyst; project coordinator | PHA staff | None | Pilot governance body | Travel only if workshop is in person | Bottom-up labor estimate | BM-01 | Moderate | A01; A12; A13 | RD-13 | 1 | 1 | 1 | 1 | 90 | 120 | 180 | 0 | 0 | 0 | 90 | 120 | 180 | RT-02 | 120 | 10800 | 14400 | 21600 | 3000 | 8000 | 18000 | 0.25 | 2700 | 3600 | 5400 | Yes | 690 | 1680 | 5940 | 17190 | 27680 | 50940 | Provisional — expert judgment | Pending participant validation | BM-01 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 17190 | 27680 | 50940 | 17190 | 27680 | 50940 | 17190 | 27680 | 50940 | 17190 | 27680 | 50940 | 17190 | 27680 | 50940 | 17190 | 27680 | 50940
WBS-01.01.02 | WBS-01.01 | State PHA | Implementation management | Implementation planning | Maintain schedule, risks, decisions, and status reporting | Operate the project-control cadence throughout implementation and pilot operations. | Current schedule, RAID log, decision log, and monthly status reports | PHA | PHA project team | Intermediary; HCCN | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | project month | IN-17 | Monthly hours × operating months | Project manager | Project coordinator; program director | PHA staff | None | Pilot governance body | Meeting and travel ODCs | Bottom-up labor estimate | BM-01 | Moderate | A64; A69 | RD-13 | 1 | 12 | 12 | 14 | 0 | 0 | 0 | 24 | 32 | 48 | 288 | 384 | 672 | RT-02 | 120 | 34560 | 46080 | 80640 | 2000 | 5000 | 12000 | 0.25 | 8640 | 11520 | 20160 | Yes | 1828 | 3831 | 13896 | 47028 | 66431 | 126696 | Provisional — expert judgment | Pending participant validation | BM-01 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 47028 | 66431 | 126696 | 47028 | 66431 | 126696 | 47028 | 66431 | 126696 | 47028 | 66431 | 126696 | 47028 | 66431 | 126696 | 47028 | 66431 | 126696
WBS-01.02.01 | WBS-01.02 | State PHA | Implementation management | Stakeholder coordination | Facilitate governance and cross-participant decision meetings | Prepare, conduct, and document site-level governance and implementation sessions. | Meeting materials, decisions, action items, and escalations | PHA | PHA project team | All funded participants | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | meeting cycle | IN-20 | Reporting cycles × hours per report | Project manager | Program director; project coordinator | PHA and participant staff | None | Executive sponsor | Meeting and travel expenses | Bottom-up labor estimate | BM-01 | Moderate | A61; A67 | RD-21 | 1 | 9 | 12 | 18 | 0 | 0 | 0 | 7.5 | 10 | 15 | 67.5 | 120 | 270 | RT-02 | 120 | 8100 | 14400 | 32400 | 0 | 0 | 0 | 0.25 | 2025 | 3600 | 8100 | Yes | 405 | 1080 | 4860 | 10530 | 19080 | 45360 | Provisional — expert judgment | Pending participant validation | BM-01 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 10530 | 19080 | 45360 | 10530 | 19080 | 45360 | 10530 | 19080 | 45360 | 10530 | 19080 | 45360 | 10530 | 19080 | 45360 | 10530 | 19080 | 45360
WBS-01.03.01 | WBS-01.03 | State PHA | Governance, legal, privacy, and security | Governance activation | Operationalize governance and decision rights | Activate decision, escalation, change-control, access-approval, and issue-resolution processes already defined in the charter. | Operating governance calendar and decision-rights matrix | PHA | PHA governance lead | Intermediary; HCCN; providers | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per site | pilot site | IN-01 | Fixed hours | Governance specialist | Project manager; legal counsel; privacy officer | PHA staff | None | Executive sponsor | None material | Bottom-up labor estimate | BM-02 | Moderate | A67 | RD-24 | 1 | 1 | 1 | 1 | 48 | 64 | 96 | 0 | 0 | 0 | 48 | 64 | 96 | RT-05 | 95 | 4560 | 6080 | 9120 | 0 | 0 | 0 | 0.25 | 1140 | 1520 | 2280 | Yes | 228 | 456 | 1368 | 5928 | 8056 | 12768 | Provisional — expert judgment | Pending participant validation | BM-02 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 5928 | 8056 | 12768 | 5928 | 8056 | 12768 | 5928 | 8056 | 12768 | 5928 | 8056 | 12768 | 5928 | 8056 | 12768 | 5928 | 8056 | 12768
WBS-01.04.01 | WBS-01.04 | State PHA | Governance, legal, privacy, and security | Agreement execution | Coordinate and review primary DUAs/DSAs | Complete site-side review and execution of the HCCN/FQHC agreement and two non-FQHC provider agreements. | Executed primary data-use or data-sharing agreements | PHA | PHA legal/privacy team | Intermediary; HCCN; provider counsel | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | primary agreement | IN-10 | Agreements × hours per agreement | Legal counsel | Privacy specialist; project manager | PHA staff | External counsel if used | Authorized signatory | External legal services if required | Bottom-up labor estimate / vendor quote | BM-03 | High | A51; A52 | RD-10 | 1 | 3 | 3 | 5 | 0 | 0 | 0 | 20.2 | 27 | 40.5 | 60.6 | 81 | 202.5 | RT-06 | 180 | 10908 | 14580 | 36450 | 0 | 0 | 25000 | 0.25 | 2727 | 3645 | 9112.5 | Yes | 545.4 | 1093.5 | 9217.5 | 14180.4 | 19318.5 | 79780 | Provisional — expert judgment | Pending participant validation | BM-03 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 14180.4 | 19318.5 | 79780 | 14180.4 | 19318.5 | 79780 | 14180.4 | 19318.5 | 79780 | 14180.4 | 19318.5 | 79780 | 14180.4 | 19318.5 | 79780 | 14180.4 | 19318.5 | 79780
WBS-01.05.01 | WBS-01.05 | State PHA | Governance, legal, privacy, and security | Privacy and de-identification approval | Approve de-identified line-level and aggregate output design | Review fields, transformations, minimum-necessary use, access, retention implementation, and disclosure controls. | Documented privacy determination and approved output specification | PHA | PHA privacy team | Intermediary; legal counsel; analytics team | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per output | output type | IN-12 | Quantity × hours per unit | Privacy specialist | Legal counsel; public health informatics lead | PHA staff | None | PHA privacy officer | External legal services if required | Bottom-up labor estimate | BM-03 | High | A22; A57; A66 | RD-25 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 16.2 | 21.6 | 32.4 | 32.4 | 43.2 | 97.2 | RT-06 | 180 | 5832 | 7776 | 17496 | 0 | 0 | 15000 | 0.25 | 1458 | 1944 | 4374 | Yes | 291.6 | 583.2 | 4874.4 | 7581.6 | 10303.2 | 41744.4 | Provisional — expert judgment | Pending participant validation | BM-03 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 7581.6 | 10303.2 | 41744.4 | 7581.6 | 10303.2 | 41744.4 | 7581.6 | 10303.2 | 41744.4 | 7581.6 | 10303.2 | 41744.4 | 7581.6 | 10303.2 | 41744.4 | 7581.6 | 10303.2 | 41744.4
WBS-01.06.01 | WBS-01.06 | State PHA | Governance, legal, privacy, and security | Security review | Approve PHA receiving connection and access controls | Review secure transport, IAM, logging, incident escalation, and use of existing PHA environments. | Connection/security approval and access-control matrix | PHA | PHA security team | Intermediary; PHA platform team | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Step-fixed | receiving system | IN-32 | Quantity × hours per unit | Security engineer | IAM specialist; privacy specialist; compliance specialist | PHA staff | Security vendor if required | PHA security authority | Incremental security tooling only if required | Bottom-up labor estimate | BM-04 | High | A49; A50; A59 | RD-09 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 16.2 | 21.6 | 32.4 | 16.2 | 21.6 | 64.8 | RT-06 | 180 | 2916 | 3888 | 11664 | 0 | 5000 | 40000 | 0.25 | 729 | 972 | 2916 | Yes | 145.8 | 666.6 | 7749.6 | 3790.8 | 10526.6 | 62329.6 | Provisional — expert judgment | Pending participant validation | BM-04 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 3790.8 | 10526.6 | 62329.6 | 3790.8 | 10526.6 | 62329.6 | 3790.8 | 10526.6 | 62329.6 | 3790.8 | 10526.6 | 62329.6 | 3790.8 | 10526.6 | 62329.6 | 3790.8 | 10526.6 | 62329.6
WBS-01.07.01 | WBS-01.07 | State PHA | Data specification and mapping | Surveillance requirements | Confirm surveillance indicators and acceptance requirements | Translate charter-defined questions into field, stratification, timeliness, quality, and usability requirements. | Approved PHA surveillance requirements and acceptance criteria | PHA | PHA public health team | Intermediary; clinical SMEs | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per output | PHA surveillance output | IN-13 | Quantity × hours per unit | Public health informatics lead | Epidemiologist; diabetes SME; business analyst | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-05 | Moderate | A17; A23 | RD-26 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 12 | 16 | 24 | 12 | 16 | 48 | RT-03 | 125 | 1500 | 2000 | 6000 | 0 | 0 | 0 | 0.25 | 375 | 500 | 1500 | Yes | 75 | 150 | 900 | 1950 | 2650 | 8400 | Provisional — expert judgment | Pending participant validation | BM-05 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 1950 | 2650 | 8400 | 1950 | 2650 | 8400 | 1950 | 2650 | 8400 | 1950 | 2650 | 8400 | 1950 | 2650 | 8400 | 1950 | 2650 | 8400
WBS-01.08.01 | WBS-01.08 | State PHA | Data specification and mapping | Clinical and analytic review | Review minimum dataset, mappings, and value-set deltas | Validate that the proposed diabetes elements and mappings support public health interpretation and approved stratifications. | PHA review comments and approval of pilot-specific data specification | PHA | PHA public health team | Intermediary; providers; measure SME | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per use case | clinical scope | IN-15 | Quantity × hours per unit | Epidemiologist | Diabetes SME; public health informatics lead | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-05 | Moderate | A14; A15; A17 | RD-27 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 12 | 16 | 24 | 12 | 16 | 24 | RT-03 | 125 | 1500 | 2000 | 3000 | 0 | 0 | 0 | 0.25 | 375 | 500 | 750 | Yes | 75 | 150 | 450 | 1950 | 2650 | 4200 | Provisional — expert judgment | Pending participant validation | BM-05 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 1950 | 2650 | 4200 | 1950 | 2650 | 4200 | 1950 | 2650 | 4200 | 1950 | 2650 | 4200 | 1950 | 2650 | 4200 | 1950 | 2650 | 4200
WBS-01.08.02 | WBS-01.08 | State PHA | Data specification and mapping | Broad cascade incremental review | Validate medication, follow-up, and utilization elements | Perform incremental review required only for the broad longitudinal diabetes cascade. | Approved broad-cascade requirements and limitations | PHA | PHA public health and clinical team | Intermediary; providers | PHA | Funded | 1B, 2B, 3B | Broad-scope increment | Fixed per use case | broad scope | IN-16 | Fixed hours | Diabetes SME | Epidemiologist; public health informatics lead | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-05 | High | A15; A20; A21; A30 | RD-02 | 0 | 1 | 1 | 1 | 64.8 | 86.4 | 129.6 | 0 | 0 | 0 | 64.8 | 86.4 | 129.6 | RT-03 | 125 | 8100 | 10800 | 16200 | 0 | 0 | 0 | 0.25 | 2025 | 2700 | 4050 | Yes | 405 | 810 | 2430 | 10530 | 14310 | 22680 | Provisional — expert judgment | Pending participant validation | BM-05 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 10530 | 14310 | 22680 | 0 | 0 | 0 | 10530 | 14310 | 22680 | 0 | 0 | 0 | 10530 | 14310 | 22680
WBS-01.09.01 | WBS-01.09 | State PHA | Configuration and integration | Receiving interface configuration | Configure existing PHA intake process | Configure secure scheduled receipt, schema validation, acknowledgments, retries, monitoring, and data loading. | Operational PHA receiving interface | PHA | PHA platform team | Intermediary; PHA security team | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Step-fixed | recipient interface | IN-09 | Interfaces × hours per interface | Data engineer | Cloud/DevOps engineer; security engineer; BI developer | PHA staff | Platform vendor if used | PHA technical lead | Incremental cloud, software, or interface fees | Bottom-up labor estimate / vendor quote | BM-07 | High | A39; A41 | RD-04 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 40.5 | 54 | 81 | 40.5 | 54 | 81 | RT-04 | 135 | 5467.5 | 7290 | 10935 | 10000 | 25000 | 60000 | 0.25 | 1366.875 | 1822.5 | 2733.75 | Yes | 773.375 | 2421.75 | 10640.25 | 17607.75 | 36534.25 | 84309 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 17607.75 | 36534.25 | 84309 | 17607.75 | 36534.25 | 84309 | 17607.75 | 36534.25 | 84309 | 17607.75 | 36534.25 | 84309 | 17607.75 | 36534.25 | 84309 | 17607.75 | 36534.25 | 84309
WBS-01.10.01 | WBS-01.10 | State PHA | Configuration and integration | Analytics configuration | Configure PHA surveillance views and data products | Configure the existing analytics environment for prevalence, A1c testing, poor control, and approved stratifications. | Configured and documented PHA analytics output | PHA | PHA analytics team | Intermediary | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per output | analytic output | IN-13 | Quantity × hours per unit | BI developer | PHA data analyst; epidemiologist; data engineer | PHA staff | Analytics vendor if used | PHA program lead | Incremental BI or platform license only if needed | Bottom-up labor estimate | BM-06 | Moderate | A17; A39; A40 | RD-16 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 12 | 16 | 24 | 12 | 16 | 48 | RT-04 | 135 | 1620 | 2160 | 6480 | 0 | 10000 | 40000 | 0.25 | 405 | 540 | 1620 | Yes | 81 | 912 | 6972 | 2106 | 13612 | 55072 | Provisional — expert judgment | Pending participant validation | BM-06 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 2106 | 13612 | 55072 | 2106 | 13612 | 55072 | 2106 | 13612 | 55072 | 2106 | 13612 | 55072 | 2106 | 13612 | 55072 | 2106 | 13612 | 55072
WBS-01.11.01 | WBS-01.11 | State PHA | Testing and remediation | PHA user acceptance | Validate line-level and aggregate outputs | Reconcile counts, stratifications, trust metadata, schema, and usability against approved acceptance criteria. | PHA user-acceptance signoff and discrepancy log | PHA | PHA analytics and public health teams | Intermediary; providers | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Per test cycle | test cycle | IN-22 | Evaluation cycles × hours per cycle | Test analyst | PHA data analyst; epidemiologist; measure SME | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-10 | High | A47; A48 | RD-06 | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 48.6 | 97.2 | 194.4 | RT-05 | 95 | 4617 | 9234 | 18468 | 0 | 0 | 0 | 0.25 | 1154.25 | 2308.5 | 4617 | Yes | 230.85 | 692.55 | 2770.2 | 6002.1 | 12235.05 | 25855.2 | Provisional — expert judgment | Pending participant validation | BM-10 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 6002.1 | 12235.05 | 25855.2 | 6002.1 | 12235.05 | 25855.2 | 6002.1 | 12235.05 | 25855.2 | 6002.1 | 12235.05 | 25855.2 | 6002.1 | 12235.05 | 25855.2 | 6002.1 | 12235.05 | 25855.2
WBS-01.12.01 | WBS-01.12 | State PHA | Testing and remediation | CMS122 validation | Validate intermediary-computed CMS122 output | Review denominator, numerator, exclusions, attribution, and discrepancies without implementing a second complete measure engine. | CMS122 validation and discrepancy report | PHA | PHA measure-validation team | Intermediary; providers | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per measure | digital measure | IN-14 | Quantity × hours per unit | Quality-measure SME | PHA data analyst; epidemiologist | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-09 | High | A16; A18 | RD-12 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 16.2 | 21.6 | 32.4 | 16.2 | 21.6 | 64.8 | RT-03 | 125 | 2025 | 2700 | 8100 | 0 | 0 | 0 | 0.25 | 506.25 | 675 | 2025 | Yes | 101.25 | 202.5 | 1215 | 2632.5 | 3577.5 | 11340 | Provisional — expert judgment | Pending participant validation | BM-09 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 2632.5 | 3577.5 | 11340 | 2632.5 | 3577.5 | 11340 | 2632.5 | 3577.5 | 11340 | 2632.5 | 3577.5 | 11340 | 2632.5 | 3577.5 | 11340 | 2632.5 | 3577.5 | 11340
WBS-01.13.01 | WBS-01.13 | State PHA | Onboarding and training | PHA user training | Train analysts, program users, and support staff | Provide role-based training on data intake, trust metadata, surveillance outputs, issue escalation, and support. | Training materials, attendance, and completion records | PHA | PHA and intermediary trainers | Intermediary | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Per cohort | training cohort | IN-27 | Training cohorts × hours per cohort | Trainer | PHA data analyst; TA specialist | PHA staff | None | PHA program lead | Training materials and travel | Bottom-up labor estimate | BM-11 | Moderate | A61 | RD-22 | 1 | 2 | 4 | 6 | 0 | 0 | 0 | 15 | 20 | 30 | 30 | 80 | 180 | RT-05 | 95 | 2850 | 7600 | 17100 | 1500 | 4000 | 10000 | 0.25 | 712.5 | 1900 | 4275 | Yes | 217.5 | 870 | 4065 | 5280 | 14370 | 35440 | Provisional — expert judgment | Pending participant validation | BM-11 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 5280 | 14370 | 35440 | 5280 | 14370 | 35440 | 5280 | 14370 | 35440 | 5280 | 14370 | 35440 | 5280 | 14370 | 35440 | 5280 | 14370 | 35440
WBS-01.14.01 | WBS-01.14 | State PHA | Pilot operations and support | Operational intake and monitoring | Operate PHA-side data receipt and issue management | Monitor scheduled loads, investigate failures, manage access, and coordinate resolution with the intermediary. | Operational logs, issue records, and accepted data loads | PHA | PHA operations and analytics teams | Intermediary | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | operating month | IN-18 | Monthly hours × operating months | Data operations analyst | Help-desk analyst; data engineer; PHA data analyst | PHA staff | Platform vendor if used | PHA technical lead | Incremental cloud and support fees | Recurring run-rate estimate | BM-13 | Moderate | A28; A29; A74; A75 | RD-14 | 1 | 6 | 9 | 9 | 0 | 0 | 0 | 18 | 24 | 36 | 108 | 216 | 324 | RT-07 | 85 | 9180 | 18360 | 27540 | 6000 | 12000 | 30000 | 0.25 | 2295 | 4590 | 6885 | Yes | 759 | 2277 | 8631 | 18234 | 37227 | 73056 | Provisional — expert judgment | Pending participant validation | BM-13 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 18234 | 37227 | 73056 | 18234 | 37227 | 73056 | 18234 | 37227 | 73056 | 18234 | 37227 | 73056 | 18234 | 37227 | 73056 | 18234 | 37227 | 73056
WBS-01.15.01 | WBS-01.15 | State PHA | Pilot operations and support | Public health analysis and action-use review | Use the pilot data and document decision utility | Analyze burden, testing, poor control, disparities, and data limitations; document how results inform public health action. | Recurring surveillance analyses and utility evidence | PHA | PHA epidemiology team | Intermediary | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | reporting cycle | IN-19 | Reporting cycles × hours per report | Epidemiologist | PHA data analyst; public health informatics lead | PHA staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-05 | Moderate | A17; A68; A72 | RD-28 | 1 | 9 | 12 | 18 | 0 | 0 | 0 | 6 | 8 | 12 | 54 | 96 | 216 | RT-03 | 125 | 6750 | 12000 | 27000 | 0 | 0 | 0 | 0.25 | 1687.5 | 3000 | 6750 | Yes | 337.5 | 900 | 4050 | 8775 | 15900 | 37800 | Provisional — expert judgment | Pending participant validation | BM-05 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800
WBS-01.16.01 | WBS-01.16 | State PHA | Evaluation, playbook, and closeout | Site evaluation | Design and execute the site-level evaluation | Collect and analyze implementation, quality, reuse, decision-utility, cost-driver, and scalability evidence. | Evaluation plan, interim findings, and final site report | PHA | PHA evaluation team | All funded participants | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | evaluation cycle | IN-21 | Evaluation cycles × hours per cycle | Evaluator | Statistician; health economist; epidemiologist; PM | PHA and participant staff | None | PHA program lead | Travel and meeting expenses | Bottom-up labor estimate | BM-14 | High | A68; A69; A71; A72; A76 | RD-17 | 1 | 3 | 4 | 6 | 0 | 0 | 0 | 67.5 | 90 | 135 | 202.5 | 360 | 810 | RT-05 | 95 | 19237.5 | 34200 | 76950 | 3000 | 8000 | 20000 | 0.25 | 4809.375 | 8550 | 19237.5 | Yes | 1111.875 | 3165 | 14542.5 | 28158.75 | 53915 | 130730 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 28158.75 | 53915 | 130730 | 28158.75 | 53915 | 130730 | 28158.75 | 53915 | 130730 | 28158.75 | 53915 | 130730 | 28158.75 | 53915 | 130730 | 28158.75 | 53915 | 130730
WBS-01.17.01 | WBS-01.17 | State PHA | Evaluation, playbook, and closeout | Playbook and transition | Develop scale recommendations and execute closeout | Document governance, implementation, evaluation, cost drivers, sustainability options, data disposition, and access transition. | Implementation playbook, transition recommendations, and closeout package | PHA | PHA project and evaluation teams | Intermediary; HCCN; providers | PHA | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Fixed per site | closeout cycle | IN-01 | Fixed hours | Technical writer | Project manager; evaluator; legal/privacy staff | PHA staff | None | Pilot governance body | Travel and publication-formatting allowance | Bottom-up labor estimate | BM-14 | Moderate | A66; A77; A78 | RD-23 | 1 | 1 | 1 | 1 | 90 | 120 | 180 | 0 | 0 | 0 | 90 | 120 | 180 | RT-05 | 95 | 8550 | 11400 | 17100 | 2000 | 6000 | 15000 | 0.25 | 2137.5 | 2850 | 4275 | Yes | 527.5 | 1305 | 4815 | 13215 | 21555 | 41190 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 13215 | 21555 | 41190 | 13215 | 21555 | 41190 | 13215 | 21555 | 41190 | 13215 | 21555 | 41190 | 13215 | 21555 | 41190 | 13215 | 21555 | 41190
WBS-02.01.01 | WBS-02.01 | HIE/HDU Intermediary | Implementation management | Technical delivery management | Manage intermediary implementation and cross-party delivery | Maintain the intermediary workplan, technical dependencies, vendor coordination, risks, and reports. | Current intermediary plan, issue log, and status reports | HDU | HDU project team | PHA; HCCN; providers; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Recurring | project month | IN-17 | Monthly hours × operating months | Project manager | Technical lead; project coordinator | HDU staff | Vendor PM as applicable | PHA project manager | Travel and indirect costs | Bottom-up labor estimate | BM-01 | Moderate | A10 | RD-21 | 1 | 12 | 12 | 14 | 0 | 0 | 0 | 27 | 36 | 54 | 324 | 432 | 756 | RT-09 | 145 | 46980 | 62640 | 109620 | 3000 | 8000 | 18000 | 0.35 | 16443 | 21924 | 38367 | Yes | 2499 | 5298 | 19143 | 68922 | 97862 | 185130 | Provisional — expert judgment | Pending participant validation | BM-01 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 68922 | 97862 | 185130 | 68922 | 97862 | 185130 | 68922 | 97862 | 185130 | 68922 | 97862 | 185130 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.02.01 | WBS-02.02 | HIE/HDU Intermediary | Governance, legal, privacy, and security | Intermediary agreement and governance support | Support agreements, governance, and access approval | Provide technical and policy exhibits, participate in agreement negotiation, and operationalize access and audit controls. | Executed agreements and operational access procedures | PHA | HDU legal/privacy team | HCCN; providers | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | primary agreement | IN-10 | Agreements × hours per agreement | Legal counsel | Privacy specialist; security engineer; project manager | HDU staff | External counsel if used | PHA legal/privacy team | External legal services if required | Bottom-up labor estimate | BM-03 | High | A51; A52 | RD-10 | 1 | 3 | 3 | 5 | 0 | 0 | 0 | 20.2 | 27 | 40.5 | 60.6 | 81 | 202.5 | RT-13 | 210 | 12726 | 17010 | 42525 | 0 | 0 | 30000 | 0.35 | 4454.1 | 5953.5 | 14883.75 | Yes | 636.3 | 1275.75 | 10878.75 | 17816.4 | 24239.25 | 98287.5 | Provisional — expert judgment | Pending participant validation | BM-03 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 17816.4 | 24239.25 | 98287.5 | 17816.4 | 24239.25 | 98287.5 | 17816.4 | 24239.25 | 98287.5 | 17816.4 | 24239.25 | 98287.5 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.03.01 | WBS-02.03 | HIE/HDU Intermediary | Governance, legal, privacy, and security | Security implementation | Configure access, logging, credentials, and incident processes | Implement pilot-specific roles, credentials, audit logging, secure transport, certificate management, and escalation procedures using existing security capabilities. | Approved and tested security configuration | HDU | HDU security team | PHA; HCCN; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Step-fixed | connection/environment | IN-07 | Interfaces × hours per interface | Security engineer | IAM specialist; DevOps engineer; compliance specialist | HDU staff | Security vendor if required | PHA security team | Incremental security tools/certificates if required | Bottom-up labor estimate | BM-04 | High | A50; A59 | RD-09 | 1 | 3 | 3 | 5 | 0 | 0 | 0 | 40.5 | 54 | 81 | 121.5 | 162 | 405 | RT-13 | 210 | 25515 | 34020 | 85050 | 0 | 10000 | 50000 | 0.35 | 8930.25 | 11907 | 29767.5 | Yes | 1275.75 | 3301.5 | 20257.5 | 35721 | 59228.5 | 185075 | Provisional — expert judgment | Pending participant validation | BM-04 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 35721 | 91547.5 | 261620 | 35721 | 91547.5 | 261620 | 35721 | 59228.5 | 185075 | 35721 | 59228.5 | 185075 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.04.01 | WBS-02.04 | HIE/HDU Intermediary | Data specification and mapping | Minimum dataset specification | Develop the pilot-specific diabetes data specification | Define required/optional elements, FHIR paths, vocabularies, provenance, timing, geography, attribution, and output use. | Approved Chronic Care Cascade Minimum Dataset Specification | HDU | HDU data standards team | PHA; HCCN; providers; measure SME | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed per clinical scope | dataset scope | IN-15 | Quantity × hours per unit | Data architect | Interoperability architect; terminology specialist; clinical SME | HDU staff | Vendor product specialists | PHA program lead | Terminology-service fees if incremental | Bottom-up labor estimate / bounded analogue | BM-08 | High | A14; A15 | RD-27 | 1 | 1 | 1 | 1 | 120 | 160 | 240 | 0 | 0 | 0 | 120 | 160 | 240 | RT-11 | 165 | 19800 | 26400 | 39600 | 0 | 5000 | 15000 | 0.35 | 6930 | 9240 | 13860 | Yes | 990 | 2355 | 8190 | 27720 | 42995 | 76650 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 27720 | 42995 | 76650 | 27720 | 42995 | 76650 | 27720 | 42995 | 76650 | 27720 | 42995 | 76650 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.05.01 | WBS-02.05 | HIE/HDU Intermediary | Data specification and mapping | Mapping and value-set delta analysis | Assess existing mappings and specify pilot deltas | Review each source configuration for A1c, diabetes diagnosis, medications, encounters, attribution, and provenance. | Source-specific mapping delta package | HDU | HDU interoperability team | Vendors; providers; HCCN | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | source configuration | IN-05 | Source configurations × hours per configuration | Interoperability architect | Terminology specialist; data analyst; clinical SME | HDU staff | Vendor product specialists | PHA public health team | Terminology and validation tools | Bottom-up labor estimate / bounded analogue | BM-07 | High | A07; A31; A37 | RD-11 | 1 | 3 | 5 | 8 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 72.9 | 162 | 388.8 | RT-11 | 165 | 12028.5 | 26730 | 64152 | 3000 | 10000 | 30000 | 0.35 | 4209.975 | 9355.5 | 22453.2 | Yes | 751.425 | 2754.75 | 14122.8 | 19989.9 | 48840.25 | 130728 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 19989.9 | 48840.25 | 130728 | 19989.9 | 48840.25 | 130728 | 19989.9 | 48840.25 | 130728 | 19989.9 | 48840.25 | 130728 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.06.01 | WBS-02.06 | HIE/HDU Intermediary | Data specification and mapping | Trust and conformance rule definition | Define diabetes-specific quality checks and release rules | Adapt existing conformance, completeness, timeliness, provenance, and audit measures; define severity and release behavior. | Pilot trust-rule specification and threshold decision log | HDU | HDU data-quality team | PHA; providers; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed plus variable | source configuration | IN-05 | Fixed hours + quantity × hours per unit | Data-quality analyst | FHIR specialist; public health informatics lead; test manager | HDU staff | Validation-tool vendor if used | PHA program lead | Validation-tool licenses if incremental | Bottom-up labor estimate / bounded analogue | BM-08 | High | A36; A47 | RD-06 | 1 | 3 | 5 | 8 | 60 | 80 | 120 | 18 | 24 | 36 | 114 | 200 | 408 | RT-12 | 120 | 13680 | 24000 | 48960 | 5000 | 15000 | 40000 | 0.35 | 4788 | 8400 | 17136 | Yes | 934 | 2925 | 13344 | 24402 | 50325 | 119440 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 24402 | 50325 | 119440 | 24402 | 50325 | 119440 | 24402 | 50325 | 119440 | 24402 | 50325 | 119440 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.07.01 | WBS-02.07 | HIE/HDU Intermediary | Configuration and integration | Architecture and interface delta review | Review existing architecture and update pilot-specific documentation | Confirm current services, data flows, environments, handoffs, and interfaces; document only necessary pilot deltas. | Approved architecture and interface-control update package | HDU | HDU architecture team | PHA; HCCN; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed plus variable | interface | IN-07 | Fixed hours + quantity × hours per unit | Solution architect | Interoperability architect; security architect; DevOps engineer | HDU staff | Vendor architects if needed | PHA technical lead | None material | Bottom-up labor estimate | BM-07 | Moderate | A33 | RD-04 | 1 | 3 | 3 | 5 | 75 | 100 | 150 | 15 | 20 | 30 | 120 | 160 | 300 | RT-11 | 165 | 19800 | 26400 | 49500 | 0 | 0 | 0 | 0.35 | 6930 | 9240 | 17325 | Yes | 990 | 1980 | 7425 | 27720 | 37620 | 74250 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 27720 | 47025 | 96525 | 27720 | 47025 | 96525 | 27720 | 37620 | 74250 | 27720 | 37620 | 74250 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.08.01 | WBS-02.08 | HIE/HDU Intermediary | Configuration and integration | Source interface configuration | Configure existing source interfaces for the pilot | Configure filters, schedules, credentials, routing, incremental behavior, acknowledgments, retries, and source-specific data contracts. | Configured and documented production source connections | HDU | HDU integration team | Providers; vendors; HCCN | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | production interface | IN-07 | Interfaces × hours per interface | Integration engineer | FHIR specialist; DevOps engineer; security engineer | HDU staff | Vendor product specialists | HDU technical lead | Interface and vendor implementation fees | Bottom-up labor estimate / vendor quote | BM-07 | High | A31; A41; A43 | RD-03 | 1 | 3 | 3 | 5 | 0 | 0 | 0 | 48 | 64 | 96 | 144 | 192 | 480 | RT-11 | 165 | 23760 | 31680 | 79200 | 50000 | 100000 | 220000 | 0.35 | 8316 | 11088 | 27720 | Yes | 3688 | 9876 | 44880 | 85764 | 152644 | 371800 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 85764 | 182740 | 443080 | 85764 | 182740 | 443080 | 85764 | 152644 | 371800 | 85764 | 152644 | 371800 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.09.01 | WBS-02.09 | HIE/HDU Intermediary | Configuration and integration | Normalization, matching, attribution, and cohort updates | Configure existing data-processing services | Apply limited diabetes-specific updates to normalization, deduplication, provider-panel attribution, and cohort logic while preserving provenance. | Validated curated diabetes cohort and attribution output | HDU | HDU data-engineering team | HCCN; providers; PHA | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed plus variable | source configuration | IN-05 | Fixed hours + quantity × hours per unit | Data engineer | MPI specialist; attribution specialist; terminology specialist | HDU staff | None | PHA measure and public health teams | Existing platform allocation; incremental compute | Bottom-up labor estimate | BM-08 | High | A19; A34 | RD-08 | 1 | 3 | 5 | 8 | 75 | 100 | 150 | 24 | 32 | 48 | 147 | 260 | 534 | RT-11 | 165 | 24255 | 42900 | 88110 | 5000 | 15000 | 40000 | 0.35 | 8489.25 | 15015 | 30838.5 | Yes | 1462.75 | 4342.5 | 19216.5 | 39207 | 77257.5 | 178165 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 39207 | 77257.5 | 178165 | 39207 | 77257.5 | 178165 | 39207 | 77257.5 | 178165 | 39207 | 77257.5 | 178165 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.09.02 | WBS-02.09 | HIE/HDU Intermediary | Configuration and integration | Broad-cascade processing increment | Configure medication, follow-up, and utilization logic | Add the incremental transformations and cohort logic required for the broad longitudinal scope. | Validated broad-cascade dataset | HDU | HDU data-engineering team | Providers; PHA | HDU | Funded | 1B, 2B, 3B | Broad-scope increment | Fixed plus variable | source configuration | IN-05 | Fixed hours + quantity × hours per unit | Data engineer | Clinical SME; terminology specialist; interoperability architect | HDU staff | Vendor specialists if required | PHA clinical team | Incremental compute and terminology services | Bottom-up labor estimate | BM-08 | High | A15; A20; A21; A30 | RD-02 | 0 | 3 | 5 | 8 | 60 | 80 | 120 | 21 | 28 | 42 | 123 | 220 | 456 | RT-11 | 165 | 20295 | 36300 | 75240 | 5000 | 15000 | 50000 | 0.35 | 7103.25 | 12705 | 26334 | Yes | 1264.75 | 3847.5 | 18786 | 33663 | 67852.5 | 170360 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 33663 | 67852.5 | 170360 | 0 | 0 | 0 | 33663 | 67852.5 | 170360 | 0 | 0 | 0 | 33663 | 67852.5 | 170360
WBS-02.10.01 | WBS-02.10 | HIE/HDU Intermediary | Configuration and integration | De-identification and aggregate-output configuration | Configure existing privacy and transformation services | Configure de-identified line-level and aggregate PHA outputs and validate reconciliation. | Approved de-identified and aggregate output processes | HDU | HDU data and privacy engineering team | PHA privacy and analytics teams | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed per output | output type | IN-12 | Quantity × hours per unit | Data engineer | Privacy specialist; database engineer; QA analyst | HDU staff | None | PHA privacy officer | Incremental storage/compute | Bottom-up labor estimate | BM-08 | High | A22; A35 | RD-25 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 16.2 | 21.6 | 32.4 | 32.4 | 43.2 | 97.2 | RT-11 | 165 | 5346 | 7128 | 16038 | 3000 | 10000 | 30000 | 0.35 | 1871.1 | 2494.8 | 5613.3 | Yes | 417.3 | 1284.6 | 6905.7 | 10634.4 | 20907.4 | 58557 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 10634.4 | 20907.4 | 58557 | 10634.4 | 20907.4 | 58557 | 10634.4 | 20907.4 | 58557 | 10634.4 | 20907.4 | 58557 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.11.01 | WBS-02.11 | HIE/HDU Intermediary | Configuration and integration | Trust layer and scorecard configuration | Configure existing trust services and source diagnostics | Implement diabetes-specific quality rules, dashboards, source reports, and release flags. | Operational trust scorecard and source-specific diagnostics | HDU | HDU data-quality and BI teams | PHA; providers; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed plus variable | source configuration | IN-05 | Fixed hours + quantity × hours per unit | Data-quality analyst | BI developer; FHIR specialist; data engineer | HDU staff | Validation vendor if used | PHA program lead | Validation and BI license increments | Bottom-up labor estimate / vendor quote | BM-08 | High | A36; A37 | RD-06 | 1 | 3 | 5 | 8 | 60 | 80 | 120 | 22.5 | 30 | 45 | 127.5 | 230 | 480 | RT-12 | 120 | 15300 | 27600 | 57600 | 10000 | 25000 | 75000 | 0.35 | 5355 | 9660 | 20160 | Yes | 1265 | 3945 | 19890 | 31920 | 66205 | 172650 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 31920 | 66205 | 172650 | 31920 | 66205 | 172650 | 31920 | 66205 | 172650 | 31920 | 66205 | 172650 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.12.01 | WBS-02.12 | HIE/HDU Intermediary | Configuration and integration | CMS122 configuration | Configure CMS122 in existing measure tooling | Implement the applicable measure version, value sets, attribution, exclusions, and result reporting. | Executable and documented CMS122 configuration | HDU | HDU measure team | PHA; providers | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed per measure | digital measure | IN-14 | Quantity × hours per unit | CQL developer | Quality-measure SME; data engineer; terminology specialist | HDU staff | Measure-engine vendor if used | PHA measure-validation team | Measure-engine or terminology license increments | Bottom-up labor estimate / vendor quote | BM-09 | High | A16; A18 | RD-12 | 1 | 1 | 1 | 2 | 120 | 160 | 240 | 0 | 0 | 0 | 120 | 160 | 240 | RT-11 | 165 | 19800 | 26400 | 39600 | 10000 | 30000 | 90000 | 0.35 | 6930 | 9240 | 13860 | Yes | 1490 | 4230 | 19440 | 38220 | 69870 | 162900 | Provisional — expert judgment | Pending participant validation | BM-09 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 38220 | 69870 | 162900 | 38220 | 69870 | 162900 | 38220 | 69870 | 162900 | 38220 | 69870 | 162900 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.13.01 | WBS-02.13 | HIE/HDU Intermediary | Configuration and integration | PHA delivery configuration | Configure secure scheduled delivery and monitoring | Configure output packaging, secure transport, acknowledgments, retries, schema checks, and delivery monitoring. | Operational intermediary-to-PHA delivery interface | HDU | HDU integration and operations teams | PHA platform/security teams | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Step-fixed | recipient interface | IN-09 | Interfaces × hours per interface | Integration engineer | Security engineer; DevOps engineer; data engineer | HDU staff | Transport vendor if used | PHA technical lead | Interface setup and recurring connection fees | Bottom-up labor estimate / vendor quote | BM-07 | High | A41 | RD-03 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 40.5 | 54 | 81 | 40.5 | 54 | 81 | RT-11 | 165 | 6682.5 | 8910 | 13365 | 10000 | 25000 | 60000 | 0.35 | 2338.875 | 3118.5 | 4677.75 | Yes | 834.125 | 2543.25 | 11004.75 | 19855.5 | 39571.75 | 89047.5 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 19855.5 | 39571.75 | 89047.5 | 19855.5 | 39571.75 | 89047.5 | 19855.5 | 39571.75 | 89047.5 | 19855.5 | 39571.75 | 89047.5 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.14.01 | WBS-02.14 | HIE/HDU Intermediary | Testing and remediation | Integrated test planning and execution | Plan and execute interface, data, security, operational, measure, and recovery tests | Coordinate test cases, test data, expected results, defects, and exit criteria across all source configurations. | Approved test plan and completed test results | HDU | HDU test team | PHA; HCCN; providers; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed plus variable | source configuration | IN-05 | Fixed hours + quantity × hours per unit | Test manager | QA analyst; security engineer; data-quality analyst | HDU staff | Vendor test support | PHA technical lead | Validation/test tools | Bottom-up labor estimate | BM-10 | High | A47; A48 | RD-29 | 1 | 3 | 5 | 8 | 75 | 100 | 150 | 18 | 24 | 36 | 129 | 220 | 438 | RT-12 | 120 | 15480 | 26400 | 52560 | 5000 | 15000 | 40000 | 0.35 | 5418 | 9240 | 18396 | Yes | 1024 | 3105 | 13884 | 26922 | 53745 | 124840 | Provisional — expert judgment | Pending participant validation | BM-10 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 26922 | 53745 | 124840 | 26922 | 53745 | 124840 | 26922 | 53745 | 124840 | 26922 | 53745 | 124840 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.15.01 | WBS-02.15 | HIE/HDU Intermediary | Testing and remediation | Baseline data-quality assessment | Run baseline conformance and data-quality assessment | Execute trust checks for each source configuration and produce source-specific diagnostic reports. | Baseline scorecard and defect register | HDU | HDU data-quality team | Providers; vendors; HCCN | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | source configuration | IN-05 | Source configurations × hours per configuration | Data-quality analyst | FHIR specialist; data analyst; clinical SME | HDU staff | Vendor support | PHA program lead | Validation-tool usage | Bottom-up labor estimate | BM-08 | High | A47; A48 | RD-06 | 1 | 3 | 5 | 8 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 72.9 | 162 | 388.8 | RT-12 | 120 | 8748 | 19440 | 46656 | 2000 | 8000 | 20000 | 0.35 | 3061.8 | 6804 | 16329.6 | Yes | 537.4 | 2058 | 9998.4 | 14347.2 | 36302 | 92984 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 14347.2 | 36302 | 92984 | 14347.2 | 36302 | 92984 | 14347.2 | 36302 | 92984 | 14347.2 | 36302 | 92984 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.16.01 | WBS-02.16 | HIE/HDU Intermediary | Testing and remediation | Coordinate remediation cycles | Triage, retest, and close source-specific defects | Issue diagnostics, coordinate fixes, reprocess data, and document results for two remediation cycles. | Completed remediation evidence and accepted residual limitations | HDU | HDU test and data-quality teams | Providers; vendors; HCCN | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | source configuration per cycle | IN-24 | Remediation cycles × source configurations × hours per cycle | Data-quality analyst | Test manager; integration engineer; project manager | HDU staff | Vendor product specialists | PHA program lead | Vendor remediation fees | Bottom-up labor estimate / vendor quote | BM-08 | High | A48 | RD-07 | 1 | 3 | 10 | 32 | 0 | 0 | 0 | 18 | 24 | 36 | 54 | 240 | 1152 | RT-12 | 120 | 6480 | 28800 | 138240 | 10000 | 30000 | 90000 | 0.35 | 2268 | 10080 | 48384 | Yes | 824 | 4410 | 34236 | 19572 | 73290 | 310860 | Provisional — expert judgment | Pending participant validation | BM-08 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 19572 | 73290 | 310860 | 19572 | 73290 | 310860 | 19572 | 73290 | 310860 | 19572 | 73290 | 310860 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.17.01 | WBS-02.17 | HIE/HDU Intermediary | Testing and remediation | Go-live readiness and cutover | Complete production readiness review and initial stabilization | Confirm legal, technical, security, data, support, rollback, and monitoring readiness; support first production cycles. | Go-live approval and first accepted production data product | PHA | HDU implementation team | All funded participants | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed per site | go-live event | IN-01 | Fixed hours | Project manager | Test manager; operations engineer; integration engineer | HDU staff | Vendor support | PHA governance body | Travel if in-person | Bottom-up labor estimate | BM-10 | High | A64 | RD-13 | 1 | 1 | 1 | 1 | 90 | 120 | 180 | 0 | 0 | 0 | 90 | 120 | 180 | RT-09 | 145 | 13050 | 17400 | 26100 | 3000 | 8000 | 20000 | 0.35 | 4567.5 | 6090 | 9135 | Yes | 802.5 | 1905 | 6915 | 21420 | 33395 | 62150 | Provisional — expert judgment | Pending participant validation | BM-10 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 21420 | 33395 | 62150 | 21420 | 33395 | 62150 | 21420 | 33395 | 62150 | 21420 | 33395 | 62150 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.18.01 | WBS-02.18 | HIE/HDU Intermediary | Onboarding and training | Participant technical onboarding | Validate readiness and onboard source organizations | Confirm contacts, technical inventory, credentials, support handoffs, and production-readiness evidence. | Completed onboarding checklist for each source organization | HDU | HDU onboarding team | Providers; HCCN; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable | organization | IN-04 | Organizations × hours per organization | Onboarding specialist | TA specialist; integration engineer; project coordinator | HDU staff | Vendor support | PHA project manager | Training materials and travel | Bottom-up labor estimate | BM-12 | Moderate | A04; A05; A61 | RD-18 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-12 | 120 | 6480 | 17280 | 54000 | 0 | 0 | 0 | 0.35 | 2268 | 6048 | 18900 | Yes | 324 | 1296 | 8100 | 9072 | 24624 | 81000 | Provisional — expert judgment | Pending participant validation | BM-12 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 9072 | 24624 | 81000 | 9072 | 24624 | 81000 | 9072 | 24624 | 81000 | 9072 | 24624 | 81000 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.19.01 | WBS-02.19 | HIE/HDU Intermediary | Onboarding and training | Operations and source-support training | Train intermediary operations and source support contacts | Train users on trust reports, error handling, escalation, monitoring, and support procedures. | Completed training and role acknowledgments | HDU | HDU training team | PHA; providers; HCCN | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Per cohort | training cohort | IN-27 | Training cohorts × hours per cohort | Trainer | TA specialist; operations engineer; data-quality analyst | HDU and participant staff | None | HDU operations lead | Training materials and travel | Bottom-up labor estimate | BM-11 | Moderate | A61 | RD-22 | 1 | 2 | 4 | 6 | 0 | 0 | 0 | 15 | 20 | 30 | 30 | 80 | 180 | RT-12 | 120 | 3600 | 9600 | 21600 | 2000 | 5000 | 12000 | 0.35 | 1260 | 3360 | 7560 | Yes | 280 | 1095 | 5040 | 7140 | 19055 | 46200 | Provisional — expert judgment | Pending participant validation | BM-11 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 7140 | 19055 | 46200 | 7140 | 19055 | 46200 | 7140 | 19055 | 46200 | 7140 | 19055 | 46200 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.20.01 | WBS-02.20 | HIE/HDU Intermediary | Pilot operations and support | Daily pipeline operations | Operate ingestion, processing, trust, measure, and delivery services | Monitor daily incremental loads, retries, backlog, quality checks, CMS122 processing, and PHA delivery. | Successful operational processing and delivery records | HDU | HDU operations team | HCCN; providers; vendors; PHA | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Recurring | operating month | IN-18 | Monthly hours × operating months | Operations engineer | SRE; data operations analyst; integration engineer | HDU staff | Vendor support | HDU operations lead | Cloud, storage, software, interface, and support fees | Recurring run-rate estimate | BM-13 | High | A28; A29; A74; A75 | RD-14 | 1 | 6 | 9 | 9 | 0 | 0 | 0 | 105 | 140 | 210 | 630 | 1260 | 1890 | RT-11 | 165 | 103950 | 207900 | 311850 | 45000 | 90000 | 180000 | 0.35 | 36382.5 | 72765 | 109147.5 | Yes | 7447.5 | 22342.5 | 73777.5 | 192780 | 393007.5 | 674775 | Provisional — expert judgment | Pending participant validation | BM-13 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 192780 | 393007.5 | 674775 | 192780 | 393007.5 | 674775 | 192780 | 393007.5 | 674775 | 192780 | 393007.5 | 674775 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.21.01 | WBS-02.21 | HIE/HDU Intermediary | Pilot operations and support | Help desk and incident resolution | Provide business-hours support and critical escalation | Resolve interface, data, access, and output issues and coordinate vendor or participant action. | Support-ticket and incident-resolution records | HDU | HDU service desk | PHA; HCCN; providers; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Variable recurring | support ticket | IN-29 | Support tickets × hours per ticket | Help-desk analyst | Operations engineer; data-quality analyst; integration engineer | HDU staff | Vendor support | HDU operations lead | Service-desk tooling if incremental | Parametric estimate | BM-13 | Moderate | A22; A61 | RD-15 | 1 | 20 | 60 | 150 | 0 | 0 | 0 | 1.9 | 2.5 | 3.8 | 38 | 150 | 570 | RT-14 | 105 | 3990 | 15750 | 59850 | 3000 | 8000 | 20000 | 0.35 | 1396.5 | 5512.5 | 20947.5 | Yes | 349.5 | 1781.25 | 11977.5 | 8736 | 31043.75 | 112775 | Provisional — expert judgment | Pending participant validation | BM-13 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 8736 | 31043.75 | 112775 | 8736 | 31043.75 | 112775 | 8736 | 31043.75 | 112775 | 8736 | 31043.75 | 112775 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.22.01 | WBS-02.22 | HIE/HDU Intermediary | Pilot operations and support | Monthly SLA and trust reporting | Produce operational and data-quality reports | Report volumes, latency, failures, completeness, conformance, provenance, incidents, and remediation status. | Monthly operational and trust reports | HDU | HDU operations and data-quality teams | PHA; source participants | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Recurring | reporting cycle | IN-19 | Reporting cycles × hours per report | Data operations analyst | Data-quality analyst; project manager | HDU staff | None | PHA program lead | None material | Bottom-up labor estimate | BM-13 | Moderate | A23; A69 | RD-30 | 1 | 9 | 12 | 18 | 0 | 0 | 0 | 6 | 8 | 12 | 54 | 96 | 216 | RT-14 | 105 | 5670 | 10080 | 22680 | 0 | 3000 | 10000 | 0.35 | 1984.5 | 3528 | 7938 | Yes | 283.5 | 981 | 4902 | 7938 | 17589 | 45520 | Provisional — expert judgment | Pending participant validation | BM-13 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 7938 | 17589 | 45520 | 7938 | 17589 | 45520 | 7938 | 17589 | 45520 | 7938 | 17589 | 45520 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.23.01 | WBS-02.23 | HIE/HDU Intermediary | Evaluation, playbook, and closeout | Technical evaluation evidence | Provide implementation, quality, reuse, support, and cost-driver evidence | Extract operational metrics, document effort and issues, participate in interviews, and analyze technical scalability. | Intermediary evaluation dataset and findings | PHA | HDU evaluation and operations teams | PHA evaluator; HCCN; providers | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Recurring | evaluation cycle | IN-21 | Evaluation cycles × hours per cycle | Evaluator | Data analyst; operations engineer; project manager; architect | HDU staff | None | PHA evaluation lead | None material | Bottom-up labor estimate | BM-14 | High | A68; A71; A72 | RD-17 | 1 | 3 | 4 | 6 | 0 | 0 | 0 | 30 | 40 | 60 | 90 | 160 | 360 | RT-12 | 120 | 10800 | 19200 | 43200 | 0 | 0 | 0 | 0.35 | 3780 | 6720 | 15120 | Yes | 540 | 1440 | 6480 | 15120 | 27360 | 64800 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 15120 | 27360 | 64800 | 15120 | 27360 | 64800 | 15120 | 27360 | 64800 | 15120 | 27360 | 64800 | 0 | 0 | 0 | 0 | 0 | 0
WBS-02.24.01 | WBS-02.24 | HIE/HDU Intermediary | Evaluation, playbook, and closeout | Technical documentation and closeout | Produce implementation notes, runbooks, source lessons, and transition records | Document reusable configuration patterns, limitations, support procedures, data disposition, and access changes. | Technical playbook content and completed intermediary closeout | HDU | HDU technical writing and project teams | PHA; HCCN; vendors | HDU | Funded | 1A, 1B, 2A, 2B | Scenario-specific | Fixed per site | closeout cycle | IN-01 | Fixed hours | Technical writer | Solution architect; project manager; operations engineer | HDU staff | None | PHA project manager | Travel if required | Bottom-up labor estimate | BM-14 | Moderate | A77; A78 | RD-23 | 1 | 1 | 1 | 1 | 90 | 120 | 180 | 0 | 0 | 0 | 90 | 120 | 180 | RT-12 | 120 | 10800 | 14400 | 21600 | 2000 | 6000 | 15000 | 0.35 | 3780 | 5040 | 7560 | Yes | 640 | 1530 | 5490 | 17220 | 26970 | 49650 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 0 | 0 | 17220 | 26970 | 49650 | 17220 | 26970 | 49650 | 17220 | 26970 | 49650 | 17220 | 26970 | 49650 | 0 | 0 | 0 | 0 | 0 | 0
WBS-03.01.01 | WBS-03.01 | HCCN | Implementation management | Member and vendor coordination | Coordinate ten FQHCs and shared vendor work | Manage member contacts, schedules, shared configuration dependencies, risks, and reporting. | Current HCCN implementation plan and member action log | HCCN | HCCN project team | FQHCs; vendors; PHA; HDU where applicable | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Recurring | project month | IN-17 | Monthly hours × operating months | Project manager | Member-services coordinator; business analyst | HCCN staff | Vendor PM | PHA project manager | Travel and participant indirects | Bottom-up labor estimate | BM-15 | High | A06; A08 | RD-21 | 1 | 12 | 12 | 14 | 0 | 0 | 0 | 24 | 32 | 48 | 288 | 384 | 672 | RT-16 | 125 | 36000 | 48000 | 84000 | 3000 | 8000 | 18000 | 0.3 | 10800 | 14400 | 25200 | Yes | 1950 | 4200 | 15300 | 51750 | 74600 | 142500 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 51750 | 74600 | 142500 | 51750 | 74600 | 142500 | 51750 | 74600 | 142500 | 51750 | 74600 | 142500
WBS-03.02.01 | WBS-03.02 | HCCN | Governance, legal, privacy, and security | HCCN/FQHC participation framework | Execute the HCCN-level agreement and member amendments | Coordinate one principal agreement and lightweight amendments/BAAs for ten FQHCs. | Executed HCCN agreement and member participation instruments | HCCN | HCCN legal/privacy team | PHA; FQHC counsel; HDU | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Variable | agreement/member | IN-11 | Agreements × hours per agreement | Legal counsel | Privacy specialist; member-services coordinator | HCCN and FQHC staff | External counsel if used | PHA legal team | External legal services | Bottom-up labor estimate | BM-03 | High | A51; A52 | RD-10 | 1 | 6 | 11 | 21 | 0 | 0 | 0 | 20.2 | 27 | 40.5 | 121.2 | 297 | 850.5 | RT-20 | 190 | 23028 | 56430 | 161595 | 0 | 0 | 30000 | 0.3 | 6908.4 | 16929 | 48478.5 | Yes | 1151.4 | 4232.25 | 28739.25 | 31087.8 | 77591.25 | 268812.75 | Provisional — expert judgment | Pending participant validation | BM-03 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 31087.8 | 77591.25 | 268812.75 | 31087.8 | 77591.25 | 268812.75 | 31087.8 | 77591.25 | 268812.75 | 31087.8 | 77591.25 | 268812.75
WBS-03.03.01 | WBS-03.03 | HCCN | Governance, legal, privacy, and security | HCCN security and access coordination | Approve member access and consolidated-feed security | Coordinate credentials, secure transport, role assignments, logging, incident procedures, and member security questions. | Approved HCCN security configuration and member procedures | HCCN | HCCN security team | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Step-fixed | shared configuration | IN-06 | Source configurations × hours per configuration | Security engineer | IAM specialist; compliance specialist; project manager | HCCN staff | Vendor security support | PHA/HDU security teams | Incremental security tools if required | Bottom-up labor estimate | BM-04 | Moderate | A08; A59 | RD-09 | 1 | 1 | 2 | 4 | 0 | 0 | 0 | 18 | 24 | 36 | 18 | 48 | 144 | RT-20 | 190 | 3420 | 9120 | 27360 | 0 | 5000 | 25000 | 0.3 | 1026 | 2736 | 8208 | Yes | 171 | 1059 | 7854 | 4617 | 17915 | 68422 | Provisional — expert judgment | Pending participant validation | BM-04 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4617 | 17915 | 68422 | 4617 | 17915 | 68422 | 4617 | 17915 | 68422 | 4617 | 17915 | 68422
WBS-03.04.01 | WBS-03.04 | HCCN | Data specification and mapping | FQHC data and panel feasibility review | Validate FQHC source coverage, panel rosters, and shared mappings | Assess two shared vendor configurations and confirm member-level provenance, attribution, and required diabetes data. | FQHC source inventory, panel roster, and mapping issues | HCCN | HCCN data team | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Variable | shared source configuration | IN-06 | Source configurations × hours per configuration | Clinical informaticist | Data architect; attribution specialist; business analyst | HCCN and FQHC staff | Vendor specialists | PHA public health team | None material | Bottom-up labor estimate | BM-15 | High | A08; A19 | RD-08 | 1 | 1 | 2 | 4 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 24.3 | 64.8 | 194.4 | RT-17 | 135 | 3280.5 | 8748 | 26244 | 0 | 0 | 0 | 0.3 | 984.15 | 2624.4 | 7873.2 | Yes | 164.025 | 656.1 | 3936.6 | 4428.675 | 12028.5 | 38053.8 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4428.675 | 12028.5 | 38053.8 | 4428.675 | 12028.5 | 38053.8 | 4428.675 | 12028.5 | 38053.8 | 4428.675 | 12028.5 | 38053.8
WBS-03.05.01 | WBS-03.05 | HCCN | Configuration and integration | Consolidated FQHC export | Configure or update one consolidated HCCN export | Aggregate the two shared FQHC configurations into a standardized member-aware export with provenance and panel context. | Validated consolidated FQHC export | HCCN | HCCN integration team | FQHC vendors; FQHCs; HDU | HCCN | Funded | 2A, 2B | Scenario-specific | Step-fixed | consolidated interface | IN-08 | Interfaces × hours per interface | Integration engineer | FHIR specialist; data engineer; attribution specialist | HCCN staff | Vendor product specialists | HDU technical lead | Vendor implementation and recurring interface fees | Bottom-up labor estimate / vendor quote | BM-15 | High | A42; A43 | RD-03 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 75 | 100 | 150 | 75 | 100 | 150 | RT-18 | 145 | 10875 | 14500 | 21750 | 30000 | 70000 | 150000 | 0.3 | 3262.5 | 4350 | 6525 | Yes | 2043.75 | 6337.5 | 25762.5 | 46181.25 | 95187.5 | 204037.5 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46181.25 | 95187.5 | 204037.5 | 46181.25 | 95187.5 | 204037.5 | 0 | 0 | 0 | 0 | 0 | 0
WBS-03.06.01 | WBS-03.06 | HCCN | Configuration and integration | HCCN-as-intermediary processing | Configure full intermediary services for Scenario 3 | Configure ingestion of two non-FQHC providers, normalization, trust, de-identification, CMS122, monitoring, and PHA delivery using HCCN infrastructure. | Operational HCCN intermediary pathway | HCCN | HCCN technical team | PHA; providers; vendors | HCCN | Funded | 3A, 3B | Scenario-specific | Fixed plus variable | source configuration/interface | IN-05 | Fixed hours + quantity × hours per unit | Solution architect | Integration engineer; data engineer; data-quality analyst; DevOps | HCCN staff | Vendor specialists | PHA technical lead | Cloud, platform, interface, validation, and measure-tool costs | Bottom-up labor estimate / vendor quote | BM-15 | Very high | A11; A34; A35; A36 | RD-05 | 0 | 3 | 5 | 8 | 150 | 200 | 300 | 45 | 60 | 90 | 285 | 500 | 1020 | RT-18 | 145 | 41325 | 72500 | 147900 | 100000 | 250000 | 600000 | 0.3 | 12397.5 | 21750 | 44370 | Yes | 7066.25 | 24187.5 | 112185 | 160788.75 | 368437.5 | 904455 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160788.75 | 368437.5 | 904455 | 160788.75 | 368437.5 | 904455
WBS-03.07.01 | WBS-03.07 | HCCN | Testing and remediation | FQHC test coordination | Coordinate test data and defects across ten FQHCs | Organize shared-vendor test runs, member-level issue review, provenance checks, and attribution reconciliation. | FQHC test evidence and member defect log | HCCN | HCCN data-quality team | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Variable | shared source configuration | IN-06 | Source configurations × hours per configuration | QA analyst | Data-quality analyst; member-services coordinator | HCCN and FQHC staff | Vendor test support | HDU/PHA test lead | Validation tools if incremental | Bottom-up labor estimate | BM-15 | High | A08; A48 | RD-06 | 1 | 1 | 2 | 4 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 24.3 | 64.8 | 194.4 | RT-19 | 105 | 2551.5 | 6804 | 20412 | 2000 | 8000 | 20000 | 0.3 | 765.45 | 2041.2 | 6123.6 | Yes | 227.575 | 1110.3 | 6061.8 | 5544.525 | 17955.5 | 52597.4 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5544.525 | 17955.5 | 52597.4 | 5544.525 | 17955.5 | 52597.4 | 5544.525 | 17955.5 | 52597.4 | 5544.525 | 17955.5 | 52597.4
WBS-03.08.01 | WBS-03.08 | HCCN | Testing and remediation | FQHC remediation coordination | Coordinate two remediation cycles across member sites | Distribute findings, assign owners, support shared fixes, collect evidence, and coordinate retesting. | Completed member remediation records | HCCN | HCCN project and data teams | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Variable | shared configuration per cycle | IN-25 | Remediation cycles × source configurations × hours per cycle | Data-quality analyst | Member-services coordinator; project manager | HCCN and FQHC staff | Vendor product specialists | HDU/PHA test lead | Vendor remediation fees | Bottom-up labor estimate / vendor quote | BM-15 | High | A48 | RD-07 | 1 | 1 | 4 | 16 | 0 | 0 | 0 | 18.2 | 24.3 | 36.5 | 18.2 | 97.2 | 584 | RT-19 | 105 | 1911 | 10206 | 61320 | 10000 | 30000 | 80000 | 0.3 | 573.3 | 3061.8 | 18396 | Yes | 595.55 | 3015.45 | 21198 | 13079.85 | 46283.25 | 180914 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13079.85 | 46283.25 | 180914 | 13079.85 | 46283.25 | 180914 | 13079.85 | 46283.25 | 180914 | 13079.85 | 46283.25 | 180914
WBS-03.09.01 | WBS-03.09 | HCCN | Onboarding and training | FQHC member onboarding | Validate and complete onboarding for ten FQHCs | Confirm participation instruments, contacts, source inventory, panels, support responsibilities, and training completion. | Completed onboarding record for each FQHC | HCCN | HCCN member-services team | FQHCs; vendors | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Variable | FQHC | IN-02 | FQHCs × hours per FQHC | Onboarding specialist | Member-services coordinator; TA specialist | HCCN and FQHC staff | Vendor support | PHA/HDU project lead | Training materials and travel | Bottom-up labor estimate | BM-15 | High | A05; A06 | RD-18 | 1 | 5 | 10 | 20 | 0 | 0 | 0 | 8.1 | 10.8 | 16.2 | 40.5 | 108 | 324 | RT-19 | 105 | 4252.5 | 11340 | 34020 | 0 | 0 | 0 | 0.3 | 1275.75 | 3402 | 10206 | Yes | 212.625 | 850.5 | 5103 | 5740.875 | 15592.5 | 49329 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5740.875 | 15592.5 | 49329 | 5740.875 | 15592.5 | 49329 | 5740.875 | 15592.5 | 49329 | 5740.875 | 15592.5 | 49329
WBS-03.10.01 | WBS-03.10 | HCCN | Onboarding and training | Member training | Train FQHC operational, IT, and clinical contacts | Provide training on source responsibilities, trust reports, remediation, incidents, and evaluation evidence. | Training materials and completion records | HCCN | HCCN training team | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Per cohort | training cohort | IN-28 | Training cohorts × hours per cohort | Trainer | Member-services coordinator; TA specialist | HCCN and FQHC staff | None | HCCN project lead | Travel and training materials | Bottom-up labor estimate | BM-11 | Moderate | A61 | RD-22 | 1 | 1 | 2 | 4 | 0 | 0 | 0 | 15 | 20 | 30 | 15 | 40 | 120 | RT-19 | 105 | 1575 | 4200 | 12600 | 2000 | 5000 | 12000 | 0.3 | 472.5 | 1260 | 3780 | Yes | 178.75 | 690 | 3690 | 4226.25 | 11150 | 32070 | Provisional — expert judgment | Pending participant validation | BM-11 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4226.25 | 11150 | 32070 | 4226.25 | 11150 | 32070 | 4226.25 | 11150 | 32070 | 4226.25 | 11150 | 32070
WBS-03.11.01 | WBS-03.11 | HCCN | Pilot operations and support | Consolidated-feed operations | Operate the HCCN feed and member support | Monitor extraction and consolidation, resolve member and vendor issues, maintain panels, and coordinate incident response. | Operational feed logs and member support records | HCCN | HCCN operations team | FQHCs; vendors; HDU/PHA | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Recurring | operating month | IN-18 | Monthly hours × operating months | Operations analyst | Help-desk analyst; data engineer; member-services coordinator | HCCN staff | Vendor support | HCCN operations lead | Platform, interface, and vendor support fees | Recurring run-rate estimate | BM-15 | High | A74; A75 | RD-14 | 1 | 6 | 9 | 9 | 0 | 0 | 0 | 54 | 72 | 108 | 324 | 648 | 972 | RT-21 | 90 | 29160 | 58320 | 87480 | 30000 | 70000 | 150000 | 0.3 | 8748 | 17496 | 26244 | Yes | 2958 | 9624 | 35622 | 70866 | 155440 | 299346 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70866 | 155440 | 299346 | 70866 | 155440 | 299346 | 70866 | 155440 | 299346 | 70866 | 155440 | 299346
WBS-03.12.01 | WBS-03.12 | HCCN | Pilot operations and support | Scenario 3 intermediary operations increment | Operate trust, CMS122, and PHA delivery in Scenario 3 | Perform the recurring intermediary functions otherwise borne by the HIE/HDU. | Scenario 3 operational reports and accepted PHA deliveries | HCCN | HCCN intermediary operations team | PHA; providers; vendors | HCCN | Funded | 3A, 3B | Scenario-specific | Recurring | operating month | IN-18 | Monthly hours × operating months | Operations engineer | Data-quality analyst; data operations analyst; help desk | HCCN staff | Platform vendor support | PHA technical lead | Cloud, software, interface, and support fees | Recurring run-rate estimate | BM-15 | Very high | A11; A40 | RD-05 | 0 | 6 | 9 | 9 | 0 | 0 | 0 | 90 | 120 | 180 | 540 | 1080 | 1620 | RT-18 | 145 | 78300 | 156600 | 234900 | 50000 | 120000 | 300000 | 0.3 | 23490 | 46980 | 70470 | Yes | 6415 | 20745 | 80235 | 158205 | 344325 | 685605 | Provisional — expert judgment | Pending participant validation | BM-15 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158205 | 344325 | 685605 | 158205 | 344325 | 685605
WBS-03.13.01 | WBS-03.13 | HCCN | Evaluation, playbook, and closeout | HCCN evaluation evidence | Document member effort, readiness, remediation, operations, and scale | Collect member-level evidence and identify shared-service efficiencies and cost drivers. | HCCN evaluation evidence and lessons learned | PHA | HCCN evaluation/project team | FQHCs; vendors; HDU | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Recurring | evaluation cycle | IN-21 | Evaluation cycles × hours per cycle | Evaluator | Project manager; member-services coordinator; data analyst | HCCN and FQHC staff | None | PHA evaluation lead | Travel | Bottom-up labor estimate | BM-14 | Moderate | A71; A72 | RD-17 | 1 | 3 | 4 | 6 | 0 | 0 | 0 | 18 | 24 | 36 | 54 | 96 | 216 | RT-19 | 105 | 5670 | 10080 | 22680 | 2000 | 6000 | 15000 | 0.3 | 1701 | 3024 | 6804 | Yes | 383.5 | 1206 | 5652 | 9754.5 | 20310 | 50136 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9754.5 | 20310 | 50136 | 9754.5 | 20310 | 50136 | 9754.5 | 20310 | 50136 | 9754.5 | 20310 | 50136
WBS-03.14.01 | WBS-03.14 | HCCN | Evaluation, playbook, and closeout | Member closeout and documentation | Complete member transition, access, data, and lessons-learned activities | Support final documentation, disposition, access changes, and member communications. | HCCN closeout package | HCCN | HCCN project team | FQHCs; vendors; PHA/HDU | HCCN | Funded | 2A, 2B, 3A, 3B | Scenario-specific | Fixed plus variable | FQHC | IN-02 | Fixed hours + quantity × hours per unit | Project manager | Technical writer; legal/privacy staff; member-services coordinator | HCCN and FQHC staff | None | PHA project manager | Travel if required | Bottom-up labor estimate | BM-14 | Moderate | A66; A77 | RD-23 | 1 | 5 | 10 | 20 | 30 | 40 | 60 | 12 | 16 | 24 | 90 | 200 | 540 | RT-16 | 125 | 11250 | 25000 | 67500 | 0 | 0 | 0 | 0.3 | 3375 | 7500 | 20250 | Yes | 562.5 | 1875 | 10125 | 15187.5 | 34375 | 97875 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 15187.5 | 34375 | 97875 | 15187.5 | 34375 | 97875 | 15187.5 | 34375 | 97875 | 15187.5 | 34375 | 97875
WBS-04.01.01 | WBS-04.01 | Healthcare Organizations & FQHCs | Implementation management | Provider participation management | Designate leads and coordinate pilot participation | Attend planning, track actions, coordinate internal IT/clinical/privacy staff, and manage vendor dependencies. | Provider participation plan and completed action items | Provider organization | Provider project lead | HCCN/HDU; vendor; PHA | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Provider IT lead | Project coordinator; clinical informaticist | Provider staff | Vendor PM | Provider executive sponsor | Participant indirect costs | Bottom-up labor estimate | BM-16 | Moderate | A04; A05; A09 | RD-21 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-26 | 95 | 5130 | 13680 | 42750 | 0 | 0 | 0 | 0.25 | 1282.5 | 3420 | 10687.5 | Yes | 256.5 | 1026 | 6412.5 | 6669 | 18126 | 59850 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850
WBS-04.02.01 | WBS-04.02 | Healthcare Organizations & FQHCs | Governance, legal, privacy, and security | Provider legal and privacy review | Review and execute participation and data-sharing instruments | Review permitted use, fields, retention implementation, de-identification, access, and liability. | Executed provider agreement or participation amendment | Provider organization | Provider legal/privacy team | PHA; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Legal counsel | Privacy specialist; provider project lead | Provider staff | External counsel if used | Provider authorized signatory | External legal services if required | Bottom-up labor estimate | BM-03 | High | A09; A51; A52 | RD-10 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 12.1 | 16.2 | 24.3 | 72.6 | 194.4 | 607.5 | RT-27 | 180 | 13068 | 34992 | 109350 | 0 | 0 | 20000 | 0.25 | 3267 | 8748 | 27337.5 | Yes | 653.4 | 2624.4 | 19402.5 | 16988.4 | 46364.4 | 176090 | Provisional — expert judgment | Pending participant validation | BM-03 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 16988.4 | 46364.4 | 176090 | 16988.4 | 46364.4 | 176090 | 16988.4 | 46364.4 | 176090 | 16988.4 | 46364.4 | 176090 | 16988.4 | 46364.4 | 176090 | 16988.4 | 46364.4 | 176090
WBS-04.03.01 | WBS-04.03 | Healthcare Organizations & FQHCs | Governance, legal, privacy, and security | Provider security and connection approval | Approve endpoint use, credentials, and incident procedures | Complete source-side security review and authorize the pilot connection or configuration. | Provider security approval and connection contacts | Provider organization | Provider security/IT team | Vendor; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Security engineer | Provider IT lead; privacy specialist | Provider staff | Vendor security support | Provider security authority | None unless vendor/security fees apply | Bottom-up labor estimate | BM-04 | Moderate | A31; A59 | RD-09 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-27 | 180 | 9720 | 25920 | 81000 | 0 | 0 | 0 | 0.25 | 2430 | 6480 | 20250 | Yes | 486 | 1944 | 12150 | 12636 | 34344 | 113400 | Provisional — expert judgment | Pending participant validation | BM-04 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 12636 | 34344 | 113400 | 12636 | 34344 | 113400 | 12636 | 34344 | 113400 | 12636 | 34344 | 113400 | 12636 | 34344 | 113400 | 12636 | 34344 | 113400
WBS-04.04.01 | WBS-04.04 | Healthcare Organizations & FQHCs | Data specification and mapping | Clinical source validation | Validate source semantics and care workflows | Review A1c, diabetes diagnosis, medications, encounters, provider panels, follow-up, and data provenance. | Provider-approved source mapping and workflow notes | Provider organization | Provider clinical informatics team | Vendor; HCCN/HDU; PHA | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Clinical informaticist | Diabetes SME; provider IT lead; data analyst | Provider staff | Vendor specialist | HCCN/HDU data team | None material | Bottom-up labor estimate | BM-16 | High | A19; A20 | RD-11 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 12.1 | 16.2 | 24.3 | 72.6 | 194.4 | 607.5 | RT-24 | 125 | 9075 | 24300 | 75937.5 | 0 | 0 | 0 | 0.25 | 2268.75 | 6075 | 18984.375 | Yes | 453.75 | 1822.5 | 11390.625 | 11797.5 | 32197.5 | 106312.5 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 11797.5 | 32197.5 | 106312.5 | 11797.5 | 32197.5 | 106312.5 | 11797.5 | 32197.5 | 106312.5 | 11797.5 | 32197.5 | 106312.5 | 11797.5 | 32197.5 | 106312.5 | 11797.5 | 32197.5 | 106312.5
WBS-04.04.02 | WBS-04.04 | Healthcare Organizations & FQHCs | Data specification and mapping | Broad-scope clinical validation | Validate medication, follow-up, and utilization definitions | Perform incremental clinical and workflow review for the broad longitudinal scope. | Approved broad-scope provider mapping and limitations | Provider organization | Provider clinical informatics team | HCCN/HDU; PHA | Provider organization | Funded | 1B, 2B, 3B | Broad-scope increment | Variable | provider organization | IN-04 | Organizations × hours per organization | Clinical informaticist | Diabetes SME; data analyst | Provider staff | Vendor specialist | PHA clinical team | None material | Bottom-up labor estimate | BM-16 | High | A15; A20; A21; A30 | RD-02 | 0 | 6 | 12 | 25 | 0 | 0 | 0 | 12.1 | 16.2 | 24.3 | 72.6 | 194.4 | 607.5 | RT-24 | 125 | 9075 | 24300 | 75937.5 | 0 | 0 | 0 | 0.25 | 2268.75 | 6075 | 18984.375 | Yes | 453.75 | 1822.5 | 11390.625 | 11797.5 | 32197.5 | 106312.5 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 11797.5 | 32197.5 | 106312.5 | 0 | 0 | 0 | 11797.5 | 32197.5 | 106312.5 | 0 | 0 | 0 | 11797.5 | 32197.5 | 106312.5
WBS-04.05.01 | WBS-04.05 | Healthcare Organizations & FQHCs | Configuration and integration | Source-system configuration support | Authorize and support vendor configuration | Provide access, approve filters and schedules, validate endpoint behavior, and coordinate source-specific implementation. | Configured and authorized source pattern | Provider organization | Provider IT team | EHR vendor; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | source configuration | IN-05 | Source configurations × hours per configuration | Provider IT lead | Clinical informaticist; security engineer | Provider staff | EHR vendor product specialist | HCCN/HDU technical lead | Vendor implementation and interface fees | Bottom-up labor estimate / vendor quote | BM-07 | High | A07; A31; A43 | RD-03 | 1 | 3 | 5 | 8 | 0 | 0 | 0 | 24.3 | 32.4 | 48.6 | 72.9 | 162 | 388.8 | RT-26 | 95 | 6925.5 | 15390 | 36936 | 40000 | 75000 | 180000 | 0.25 | 1731.375 | 3847.5 | 9234 | Yes | 2346.275 | 6779.25 | 32540.4 | 51003.15 | 101016.75 | 258710.4 | Provisional — expert judgment | Pending participant validation | BM-07 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 51003.15 | 101016.75 | 258710.4 | 51003.15 | 101016.75 | 258710.4 | 51003.15 | 101016.75 | 258710.4 | 51003.15 | 101016.75 | 258710.4 | 51003.15 | 101016.75 | 258710.4 | 51003.15 | 101016.75 | 258710.4
WBS-04.06.01 | WBS-04.06 | Healthcare Organizations & FQHCs | Configuration and integration | Panel and roster preparation | Provide and reconcile provider-panel attribution data | Extract, validate, and correct provider rosters and patient panels required for cohort and measure logic. | Validated attribution roster and exception log | Provider organization | Provider operations/data team | HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Data analyst | Provider IT lead; clinical informaticist | Provider staff | Vendor specialist if needed | HCCN/HDU attribution specialist | None material | Bottom-up labor estimate | BM-16 | High | A19 | RD-08 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 12.1 | 16.2 | 24.3 | 72.6 | 194.4 | 607.5 | RT-26 | 95 | 6897 | 18468 | 57712.5 | 0 | 0 | 0 | 0.25 | 1724.25 | 4617 | 14428.125 | Yes | 344.85 | 1385.1 | 8656.875 | 8966.1 | 24470.1 | 80797.5 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 8966.1 | 24470.1 | 80797.5 | 8966.1 | 24470.1 | 80797.5 | 8966.1 | 24470.1 | 80797.5 | 8966.1 | 24470.1 | 80797.5 | 8966.1 | 24470.1 | 80797.5 | 8966.1 | 24470.1 | 80797.5
WBS-04.07.01 | WBS-04.07 | Healthcare Organizations & FQHCs | Testing and remediation | Source testing and baseline review | Review pilot extracts and baseline diagnostics | Validate transmitted data, investigate discrepancies, and confirm source-specific trust findings. | Provider test signoff and baseline issue list | Provider organization | Provider IT/clinical team | Vendor; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | QA analyst | Clinical informaticist; provider IT lead; data analyst | Provider staff | Vendor test support | HCCN/HDU test lead | Vendor test fees if applicable | Bottom-up labor estimate | BM-16 | High | A47; A48 | RD-06 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 12.1 | 16.2 | 24.3 | 72.6 | 194.4 | 607.5 | RT-26 | 95 | 6897 | 18468 | 57712.5 | 5000 | 15000 | 40000 | 0.25 | 1724.25 | 4617 | 14428.125 | Yes | 594.85 | 2510.1 | 14656.875 | 14216.1 | 40595.1 | 126797.5 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 14216.1 | 40595.1 | 126797.5 | 14216.1 | 40595.1 | 126797.5 | 14216.1 | 40595.1 | 126797.5 | 14216.1 | 40595.1 | 126797.5 | 14216.1 | 40595.1 | 126797.5 | 14216.1 | 40595.1 | 126797.5
WBS-04.08.01 | WBS-04.08 | Healthcare Organizations & FQHCs | Testing and remediation | Source remediation | Correct source configuration or documentation issues | Work with vendors to resolve mappings, missingness, schedules, panel, and transmission defects and support retesting. | Completed provider remediation evidence | Provider organization | Provider IT/clinical team | Vendor; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization per cycle | IN-26 | Remediation cycles × source configurations × hours per cycle | Provider IT lead | Clinical informaticist; data analyst | Provider staff | Vendor product specialist | HCCN/HDU test lead | Vendor remediation fees | Bottom-up labor estimate / vendor quote | BM-16 | High | A48 | RD-07 | 1 | 3 | 10 | 32 | 0 | 0 | 0 | 12 | 16 | 24 | 36 | 160 | 768 | RT-26 | 95 | 3420 | 15200 | 72960 | 20000 | 50000 | 150000 | 0.25 | 855 | 3800 | 18240 | Yes | 1171 | 4890 | 33444 | 25446 | 73890 | 274644 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 25446 | 73890 | 274644 | 25446 | 73890 | 274644 | 25446 | 73890 | 274644 | 25446 | 73890 | 274644 | 25446 | 73890 | 274644 | 25446 | 73890 | 274644
WBS-04.09.01 | WBS-04.09 | Healthcare Organizations & FQHCs | Onboarding and training | Provider onboarding | Complete legal, technical, operational, and support onboarding | Provide contacts, inventory, agreements, rosters, credentials, support paths, and readiness evidence. | Completed provider onboarding checklist | Provider organization | Provider project team | HCCN/HDU; vendor | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Provider IT lead | Project coordinator; privacy/security; clinical informaticist | Provider staff | Vendor support | HCCN/HDU onboarding lead | Travel and training materials | Bottom-up labor estimate | BM-12 | Moderate | A04; A05; A61 | RD-18 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-26 | 95 | 5130 | 13680 | 42750 | 1000 | 3000 | 8000 | 0.25 | 1282.5 | 3420 | 10687.5 | Yes | 306.5 | 1251 | 7612.5 | 7719 | 21351 | 69050 | Provisional — expert judgment | Pending participant validation | BM-12 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 7719 | 21351 | 69050 | 7719 | 21351 | 69050 | 7719 | 21351 | 69050 | 7719 | 21351 | 69050 | 7719 | 21351 | 69050 | 7719 | 21351 | 69050
WBS-04.10.01 | WBS-04.10 | Healthcare Organizations & FQHCs | Onboarding and training | Provider staff training | Train source, clinical, and support contacts | Participate in training on data responsibilities, trust diagnostics, remediation, incidents, and evaluation evidence. | Provider training completion records | Provider organization | Provider staff | HCCN/HDU trainer | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Provider IT lead | Clinical informaticist; support contact | Provider staff | None | Provider project lead | Travel if required | Bottom-up labor estimate | BM-11 | Moderate | A61 | RD-22 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-26 | 95 | 5130 | 13680 | 42750 | 0 | 0 | 0 | 0.25 | 1282.5 | 3420 | 10687.5 | Yes | 256.5 | 1026 | 6412.5 | 6669 | 18126 | 59850 | Provisional — expert judgment | Pending participant validation | BM-11 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850
WBS-04.11.01 | WBS-04.11 | Healthcare Organizations & FQHCs | Pilot operations and support | Source operations and incident response | Maintain source jobs and resolve operational issues | Monitor source-side processes, maintain credentials, respond to incidents, and support data-quality investigations. | Provider operational support and incident records | Provider organization | Provider IT/support team | Vendor; HCCN/HDU | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | provider organization per month | IN-30 | Monthly hours × operating months | Provider IT lead | Help-desk analyst; clinical informaticist | Provider staff | Vendor support | Provider operations lead | Recurring vendor/interface fees | Recurring run-rate estimate | BM-13 | Moderate | A74; A75 | RD-14 | 1 | 36 | 108 | 225 | 0 | 0 | 0 | 3 | 4 | 6 | 108 | 432 | 1350 | RT-26 | 95 | 10260 | 41040 | 128250 | 20000 | 50000 | 120000 | 0.25 | 2565 | 10260 | 32062.5 | Yes | 1513 | 6828 | 37237.5 | 34338 | 108128 | 317550 | Provisional — expert judgment | Pending participant validation | BM-13 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 34338 | 108128 | 317550 | 34338 | 108128 | 317550 | 34338 | 108128 | 317550 | 34338 | 108128 | 317550 | 34338 | 108128 | 317550 | 34338 | 108128 | 317550
WBS-04.12.01 | WBS-04.12 | Healthcare Organizations & FQHCs | Pilot operations and support | Clinical/data-quality investigation support | Review source-specific quality and plausibility issues | Participate in recurring investigation of missingness, clinical plausibility, panel changes, and measure discrepancies. | Resolved or documented data-quality issues | Provider organization | Provider clinical informatics team | HCCN/HDU; PHA | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Recurring | reporting cycle | IN-19 | Reporting cycles × hours per report | Clinical informaticist | Data analyst; provider IT lead | Provider staff | Vendor specialist as needed | HCCN/HDU data-quality lead | None material | Bottom-up labor estimate | BM-16 | Moderate | A47; A71 | RD-06 | 1 | 9 | 12 | 18 | 0 | 0 | 0 | 6 | 8 | 12 | 54 | 96 | 216 | RT-24 | 125 | 6750 | 12000 | 27000 | 0 | 0 | 0 | 0.25 | 1687.5 | 3000 | 6750 | Yes | 337.5 | 900 | 4050 | 8775 | 15900 | 37800 | Provisional — expert judgment | Pending participant validation | BM-16 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800 | 8775 | 15900 | 37800
WBS-04.13.01 | WBS-04.13 | Healthcare Organizations & FQHCs | Evaluation, playbook, and closeout | Provider evaluation participation | Provide effort, burden, workflow, and utility evidence | Participate in interviews, submit effort and support data, validate lessons, and identify scaling implications. | Provider evaluation evidence and feedback | PHA | Provider project and clinical teams | HCCN/HDU evaluator | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization per evaluation cycle | IN-31 | Evaluation cycles × hours per cycle | Provider project lead | Clinical informaticist; finance analyst; provider IT lead | Provider staff | None | PHA evaluation lead | Travel if required | Bottom-up labor estimate | BM-14 | Moderate | A71; A72 | RD-17 | 1 | 18 | 48 | 150 | 0 | 0 | 0 | 7.5 | 10 | 15 | 135 | 480 | 2250 | RT-26 | 95 | 12825 | 45600 | 213750 | 1000 | 3000 | 8000 | 0.25 | 3206.25 | 11400 | 53437.5 | Yes | 691.25 | 3645 | 33262.5 | 17722.5 | 63645 | 308450 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 17722.5 | 63645 | 308450 | 17722.5 | 63645 | 308450 | 17722.5 | 63645 | 308450 | 17722.5 | 63645 | 308450 | 17722.5 | 63645 | 308450 | 17722.5 | 63645 | 308450
WBS-04.14.01 | WBS-04.14 | Healthcare Organizations & FQHCs | Evaluation, playbook, and closeout | Provider closeout | Complete access, data, contract, and operational closeout | Confirm final data handling, access termination or transition, outstanding issue ownership, and final invoicing. | Provider closeout confirmation | Provider organization | Provider project/legal/IT teams | HCCN/HDU; PHA | Provider organization | Funded | 1A, 1B, 2A, 2B, 3A, 3B | Base common | Variable | provider organization | IN-04 | Organizations × hours per organization | Provider project lead | Legal counsel; privacy specialist; provider IT lead | Provider staff | None | PHA project manager | None material | Bottom-up labor estimate | BM-14 | Moderate | A66; A78 | RD-23 | 1 | 6 | 12 | 25 | 0 | 0 | 0 | 9 | 12 | 18 | 54 | 144 | 450 | RT-26 | 95 | 5130 | 13680 | 42750 | 0 | 0 | 0 | 0.25 | 1282.5 | 3420 | 10687.5 | Yes | 256.5 | 1026 | 6412.5 | 6669 | 18126 | 59850 | Provisional — expert judgment | Pending participant validation | BM-14 | Provisional Stage 4 assumption; replace with actual rate, quote, or validated benchmark where available. | 1 | 1 | 1 | 1 | 1 | 1 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850 | 6669 | 18126 | 59850

## Optional Add-Ons Build-Up (hidden)
Optional Add-Ons and Sensitivity Packages
These packages are excluded from the base scenario unless their trigger occurs.
Add-On ID | Add-On | Trigger | Incremental WBS Activities | Organizations Affected | Formula Structure | Scaling Variables | Benchmark / Estimating Method | Dependencies | Exclusions / Risks | Active? | Applicable Scenario(s) | Low Labor | Base Labor | High Labor | Low Non-Labor | Base Non-Labor | High Non-Labor | Indirect Rate | Low Contingency | Base Contingency | High Contingency | Low Incremental Total | Base Incremental Total | High Incremental Total | BOE Status | Validation Status | Source ID
ADD-01 | UDS+ interface and support | Charter includes UDS+ and no adequate existing pathway is available | Requirements/mapping; HRSA authentication; interface configuration; test submission; error remediation; operating support | HCCN; FQHCs; HIE/HDU where applicable | Fixed hours + interface × hours per interface + monthly support × months + vendor fees | 1 interface; FQHC count; test cycles; operating months | Vendor quote; bounded UDS+ implementation analogue | Current UDS+ IG; HRSA test environment; FQHC attribution; agreements | Excludes HRSA federal effort and long-term operations | No | All | 120000 | 220000 | 400000 | 50000 | 150000 | 350000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — bounded component | Quote required | BM-07
ADD-02 | Closed-loop chronic-care referral analysis | Charter includes referral add-on and an existing referral platform/governance model is operational | Workflow confirmation; data-element mapping; marginal platform configuration; test referral/status exchange; analytic and evaluation updates | PHA; intermediary; providers; referral platform/CBO | Fixed workflow effort + participants × onboarding hours + interface/configuration fee | Referral organizations; workflows; test cycles | Bottom-up labor; vendor quote; component analogue | Existing platform, agreements, consent-aware workflow, participating referral recipient | Excludes new referral infrastructure or broad consent-management implementation | No | All | 50000 | 100000 | 220000 | 10000 | 35000 | 100000 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — expert judgment | Decision required
ADD-03 | New MedicationDispense connection | Broad scope requires dispensing data not already available | Data-source agreement; pharmacy/payer interface; mapping; matching; testing; trust rules; operations | Intermediary; PHA; providers; pharmacy/payer source | Fixed source onboarding + interface × hours + monthly fee × months | 1 new data source/interface; operating months; transaction fees | Vendor quote; public interface fee; bottom-up labor | Data owner participation, legal authority, matching method | Excluded from base; may materially alter schedule | No | 1B, 2B, 3B | 100000 | 220000 | 450000 | 75000 | 200000 | 500000 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — vendor quote needed | Quote required | BM-07
ADD-04 | Additional non-FQHC healthcare organization | Participant count exceeds two | Agreement; onboarding; source review; configuration; testing; remediation; training; operations; evaluation | PHA; intermediary/HCCN; added provider; vendor | Organization × hours per organization + source/interface increment where unique | Provider count; source configurations; interfaces; operating months | Parametric estimate using PROV WBS and interface units | Existing connectivity and vendor availability | Does not include new source configuration unless separately triggered | No | All | 25000 | 50000 | 95000 | 5000 | 15000 | 40000 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — parametric | Pending participant validation | BM-16
ADD-05 | Additional FQHC | FQHC count exceeds ten | Participation amendment; member onboarding; panel validation; training; operations; evaluation | HCCN; added FQHC; vendor; PHA/HDU | FQHCs × hours per FQHC + marginal support × months | FQHC count; training cohorts; operations months | Parametric estimate using HCCN and PROV WBS | Same HCCN and existing shared vendor pattern | If a new vendor pattern is introduced, also apply ADD-06 | No | 2A, 2B, 3A, 3B | 12000 | 25000 | 50000 | 2000 | 6000 | 15000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — parametric | Pending HCCN validation | BM-15
ADD-06 | Additional source-system configuration | More than five distinct configurations or a materially different tenant pattern | Mapping assessment; interface/configuration; trust rules; testing; baseline; remediation; support | Intermediary/HCCN; affected providers; vendor | Source configurations × hours per configuration + cycles × hours per configuration | Source configuration count; remediation cycles | Parametric estimate; vendor quote | Endpoint and vendor documentation | May also add a production interface | No | All | 45000 | 90000 | 170000 | 15000 | 35000 | 90000 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — parametric | Quote required | BM-07
ADD-07 | Additional production interface | Interface topology exceeds scenario base | Architecture delta; connection/security setup; configuration; testing; monitoring; recurring support | Intermediary/HCCN; provider/vendor; PHA if recipient interface | Interfaces × setup hours + monthly fee × months | Interface count; environments; operations months | Vendor quote; bounded interface analogue | Existing endpoint and data-use authority | Separate from source mapping where the same configuration is reused | No | All | 35000 | 70000 | 140000 | 15000 | 35000 | 80000 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — parametric | Quote required | BM-07
ADD-08 | Additional remediation cycle | Two base remediation cycles are insufficient | Defect triage; participant/vendor coordination; corrections; reprocessing; retesting; reporting | Intermediary/HCCN; providers; vendors; PHA | Source configurations × additional cycles × hours per cycle + vendor fees | Source configurations; added cycles | Parametric estimate based on base remediation WBS | Baseline severity and vendor availability | Do not duplicate defects covered by fixed-fee vendor implementation | No | All | 30000 | 65000 | 140000 | 10000 | 30000 | 90000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — parametric | Pending baseline | BM-08
ADD-09 | Six-month operations sensitivity | Schedule permits only six live months or sponsor chooses shorter evidence period | Reduce recurring operations, support, reporting, and evaluation cycles; preserve fixed implementation cost | All funded organizations | Monthly run-rate × 6 instead of × 9 | Operations months; reporting cycles; evaluation cycles | Recurring run-rate estimate | Approved evaluation plan and revised schedule | Not a simple 33% reduction of total project cost because fixed costs remain | No | All | -180000 | -320000 | -520000 | -60000 | -120000 | -220000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Schedule sensitivity | Decision required | BM-13
ADD-10 | Formal security authorization or penetration testing | PHA/intermediary requires ATO-equivalent approval, independent assessment, or new control documentation | Security plan; control evidence; assessment coordination; remediation; authorization package | PHA; intermediary/HCCN; providers/vendors as needed | Fixed authorization effort + systems × evidence hours + external assessment fee | Systems; environments; findings/remediation cycles | Vendor quote; bottom-up security labor | Security authority requirements and environment inventory | Excluded from base standard connection review | No | All | 80000 | 180000 | 400000 | 50000 | 150000 | 400000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — vendor quote needed | Security decision required | BM-04
ADD-11 | New environment or software license | Existing environment capacity or licenses are insufficient | Provision environment; deploy/configure; security review; testing; backup/monitoring; recurring licenses | PHA; intermediary/HCCN | Environments × setup hours + monthly cloud/license fee × months | Environment count; license units; months | Public rate schedule; vendor quote; cloud calculator | Architecture, security requirements, licensing terms | Avoid allocating sunk enterprise costs unless full-economic-cost view is requested | No | All | 50000 | 110000 | 250000 | 60000 | 150000 | 400000 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — vendor quote needed | Technical validation required | BM-13
ADD-12 | High-intensity technical assistance | Readiness validation identifies material participant capability gaps | Additional readiness sessions; documentation support; hands-on mapping/testing; repeated training | PHA; intermediary/HCCN; providers | Organizations × additional TA hours per organization | Organizations; TA intensity; months | Bottom-up labor; historical internal estimate | Specific gap-resolution plan | Does not include net-new platform development | No | All | 40000 | 90000 | 200000 | 5000 | 15000 | 40000 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Provisional — bottom-up | Readiness validation required | BM-12