# Cost Model Benchmarks and Basis of Estimate
for the Chronic Care Cascade Pilot

Benchmark report and cost-model narrative

# 1. Executive Summary

The closest publicly documented analogs for the Chronic Care Cascade pilot are not one-for-one “chronic care cascade” projects, but a cluster of adjacent investments: HRSA Health Center Controlled Network programs, CDC MENDS work, ONC LEAP FHIR pilots, APHL public-health exchange infrastructure, and federal FHIR service contracts. Taken together, they show a recurring pattern: the major spend is usually not raw cloud or API transaction cost, but intermediary operations, participant onboarding and remediation, trust and data-quality work, governance, and multi-party support. That pattern aligns with the Stage 1 pilot design, which centers on reusing existing HIE/HDU/HCCN capabilities, adding only modest technical updates, and focusing funding on turning existing exchange assets into trustworthy reusable data products for public health, UDS+, and quality uses. [1]

For whole-project analogs, the strongest official benchmark is HRSA’s FY25 HCCN program: roughly $48 million to fund 49 HCCNs over August 1, 2025 to July 31, 2028, or about $326,531 per HCCN-year on average. That program’s required objectives—data management and analytics, interoperability/data sharing, and UDS+ implementation—map directly to the pilot’s participant-side work. State-level HCCN examples show materially different per-center support levels: $520,000 for 10 participating health centers in Minnesota and $650,000 for 19 participating health centers in Colorado, implying roughly $52,000 and $34,211 per participating health center respectively in those award examples. Those are not pilot prices, but they are very useful public proxies for the scale of network-level funding required to coordinate FQHC-heavy implementation. [2]

For public-health/intermediary analogs, the official CDC and APHL sources are especially useful. CDC’s MENDS publications describe a five-site distributed chronic-disease surveillance model covering 91 health system and clinic partners and approximately 10 million patients, with implementation emphasis on governance, technical infrastructure, chronic disease algorithms, validation, weighting/modeling, and workforce education. A related CDC paper reports a connected $1.8 million financial-assistance award for MENDS validation work, while ONC’s 2023 LEAP program awarded $2 million across two projects for advanced FHIR and FHIR data-quality work—effectively $1 million per project over two years. APHL’s AIMS+ OTC-reporting contract was up to $8.8 million over three years, showing the scale of a centrally managed public-health intermediary service, while APHL also reports that national eCR infrastructure optimization reduced AWS costs by roughly $258,000 per month at national scale. These analogs imply that once a pilot goes beyond simple reuse into serious validation, shaping, and managed interoperability services, costs move quickly from “minor interface tuning” into six- and seven-figure program territory. [3]

The best component benchmarks suggest four practical default views for the Stage 2 base scenario. First, if the pilot truly reuses existing exchange pathways, per-source technical setup may be closer to tens of hours than to a net-new interface build; published FHIR implementation examples show 4–40 hours for straightforward standardized setup, while more complex one-time algorithm implementation can take 200–250 hours at the first site and then drop to roughly 20 hours when reused in the same EHR environment. Second, if UDS+ is included, public FY24 QIA-UDS+ award pages suggest a reasonable per-health-center benchmark band of roughly $32,000–$62,000, with observed sampled awards reaching $82,794 in one state page. Third, recurring operating support for smaller exchanges is often priced as support plans or per-clinician fees rather than bespoke engineering: NCHIIN’s published fee schedule includes $450 per clinician-year, $0.06 per result delivered for hospitals/labs, 20% of interface development cost as annual interface maintenance after year one, and network support plans from $145 to $400 per month or $85 per hour ad hoc. Fourth, for a modest one-site pilot, public cloud storage is unlikely to be a primary cost driver; official cloud sources show commodity storage and request pricing that are trivial compared with labor, though logging and monitoring can grow if observability is overbuilt. [4]

The most defensible default modeling stance for the base scenario is therefore this: treat governance/chartering as pre-pilot and unfunded; treat technical architecture, interfaces, normalization, deduplication, de-identification, and trust-layer functions as mostly existing; assume new funding primarily covers implementation planning, partner onboarding, source-specific mapping and remediation, trust/reporting adjustments, quality-measure output work, training, pilot operations, and evaluation; and model UDS+ and referral functions as explicit option switches rather than baked-in base scope. That posture is consistent with the pilot documents and with the strongest Analog evidence. [5]

# 2. Pilot and Scenario Scope

The pilot fit criteria came from the pilot materials: intermediary-centered exchange, chronic-care surveillance, reusable datasets for multiple consumers, a shared trust layer, optional UDS+, optional referral add-on, and a one-year pilot window. For this report, we assumed that most interfaces and technical assets already exist, so the most relevant analogs are not “greenfield HIE builds,” but programs that funded onboarding, value realization, trust, validation, reporting use cases, and modest configuration changes on top of existing exchange infrastructure.

For our pricing research, we worked from the following base scenario: one funded state-PHA site, HIE/HDU with HCCN consolidation, 10 FQHCs plus 2 other providers, 5 source configurations, narrow A1c base case, and nine months of live operation. Public benchmarks were therefore screened for usefulness in one of four ways: total program scale, provider/network onboarding scale, interface/mapping/remediation effort, or recurring operations/support scale. Where public sources did not expose an exact value for a pilot component, we preserved the uncertainty and recommended a conservative placeholder or a parameter range rather than fabricating precision. [7]

The cost model evaluates six structural scenarios. The letter identifies dataset scope (A = narrow A1c-focused; B = broad longitudinal cascade), and the number identifies the intermediary operating model.

| Scenario | Intermediary model | Provider structure | Dataset scope | Operations | Key distinction |
| --- | --- | --- | --- | --- | --- |
| 1A | HIE/HDU without HCCN | 10 FQHCs + 2 healthcare organizations connect without HCCN consolidation | Narrow A1c-focused | 9 months | Most source connections; no HCCN managed-services layer |
| 1B | HIE/HDU without HCCN | Same as 1A | Broad longitudinal diabetes cascade | 9 months | Adds broader data, mapping, analytics, and validation |
| 2A | HIE/HDU with HCCN | HCCN consolidates 10 FQHCs; 2 healthcare organizations connect directly | Narrow A1c-focused | 9 months | HCCN adds managed services and reduces production interfaces |
| 2B | HIE/HDU with HCCN | Same as 2A | Broad longitudinal diabetes cascade | 9 months | Broad scope plus two intermediary/aggregation layers |
| 3A | HCCN acting as intermediary | HCCN ingests 10 FQHCs and 2 healthcare organizations; no HIE/HDU | Narrow A1c-focused | 9 months | HCCN performs full intermediary, trust, and PHA delivery functions |
| 3B | HCCN acting as intermediary | Same as 3A | Broad longitudinal diabetes cascade | 9 months | Broad scope delivered entirely through HCCN intermediary model |

# 3. Pilot Products

The spreadsheet product register is consolidated below so that the narrative report—not the executive estimating workbook—serves as the primary description of what the funded pilot is expected to produce. Product wording is retained from the cost model.

| Product area | Deliverable or milestone | Description | Responsible organization | Timing |
| --- | --- | --- | --- | --- |
| A. Governance, planning, and readiness products | Pilot Charter — pre-award, not funded | Establishes the fixed scope and operating parameters that applicants or selected pilot teams will implement. The charter includes: selected intermediary model; PHA surveillance questions, outputs, and action-use cases; narrow versus broad longitudinal dataset scope; UDS+ decision; referral add-on decision; partner and system inventory; readiness attestations; and data-retention and closeout plans | CDC / National Partner pilot leadership, with input from the selected or prospective PHA and intermediary | Completed before the funded pilot period begins |
| A. Governance, planning, and readiness products | Pilot Implementation Plan — funded | Converts the approved charter into an executable plan covering workstreams, activities, owners, schedule, dependencies, milestones, risks, reporting cadence, testing, operations, evaluation, and closeout | PHA and intermediary jointly | Initial version during Month 1; updated as needed during mobilization |
| A. Governance, planning, and readiness products | Detailed project schedule and milestone baseline | Establishes the funded project timeline, including governance completion, configuration, testing, onboarding, go-live, operations, evaluation, and closeout | Pilot project manager | Month 1 |
| A. Governance, planning, and readiness products | Responsibility assignment matrix | Defines accountable, responsible, consulted, and informed parties for each funded activity and deliverable | Pilot project manager | Month 1 |
| A. Governance, planning, and readiness products | Risk, issue, assumption, and decision log | Tracks scope, readiness, governance, vendor, data-quality, operational, and evaluation risks and decisions | Pilot project manager | Established Month 1; maintained throughout pilot |
| A. Governance, planning, and readiness products | Participant onboarding and engagement plan | Defines how the PHA, intermediary, HCCN, healthcare organizations, FQHCs, and vendors will be mobilized and supported | Intermediary and HCCN, coordinated with PHA | Month 1–2 |
| A. Governance, planning, and readiness products | Readiness validation and gap-resolution plan | Validates the pre-pilot readiness attestations and identifies any limited remediation required before data-use testing begins. This is not a full readiness assessment or partner-selection activity | Intermediary and PHA | Month 1–2 |
| A. Governance, planning, and readiness products | Governance implementation workplan | Operationalizes the governance model established in the charter, including meeting cadence, decision processes, change control, access approvals, escalation, and oversight responsibilities | PHA | Month 1–2 |
| A. Governance, planning, and readiness products | Evaluation implementation plan | Converts the charter’s intended outcomes into site-level measures, evidence sources, baselines, data-collection responsibilities, and reporting cadence | PHA or site evaluation lead | Month 1–2 |
| B. Legal, privacy, security, and governance deliverables | Governance charter and decision-rights matrix | Defines control over dataset changes, measure logic, access, remediation, issue escalation, publication, and transition | PHA | Months 1–2 |
| B. Legal, privacy, security, and governance deliverables | Primary DUAs/DSAs | One agreement for the HCCN/FQHC group, plus one for each of the two independent healthcare organizations | PHA and participant legal teams | Target completion by end of Month 2 |
| B. Legal, privacy, security, and governance deliverables | FQHC participation amendments/BAAs | Lightweight agreements binding the ten FQHCs to the HCCN-level arrangement | HCCN and FQHCs | Months 1–2 |
| B. Legal, privacy, security, and governance deliverables | Privacy and de-identification determination | Defines what remains identifiable within the intermediary and what is delivered as de-identified line-level or aggregate data | PHA privacy office and intermediary | Months 1–3 |
| B. Legal, privacy, security, and governance deliverables | Security and access-control plan | Defines secure transport, authentication, authorization, RBAC, logging, incident management, and environment access | Intermediary and PHA security teams | Months 2–3 |
| B. Legal, privacy, security, and governance deliverables | Data-retention and closeout plan | Establishes pilot-period retention, destruction or transition, archival rules, and access termination | PHA and intermediary | Before go-live; finalized at closeout |
| C. Technical and data deliverables | Chronic Care Cascade Minimum Dataset Specification | Defines the diabetes data elements, definitions, provenance, timestamps, geography, attribution requirements, and consumer mappings needed for the selected narrow or broad scope | Intermediary / data standards lead | Months 1–3 |
| C. Technical and data deliverables | Existing-data mapping assessment and targeted FHIR mapping updates | Reviews existing source mappings and identifies only the additions or changes needed to support the selected diabetes dataset, PHA output, and CMS122 | Intermediary | Months 1–3 |
| C. Technical and data deliverables | FHIR mapping guide and value-set delta documentation | Produces a pilot-specific supplement to existing mapping documentation rather than rebuilding a complete mapping guide from scratch | Intermediary | Months 2–3 |
| C. Technical and data deliverables | Conformance and validation rule updates | Adapts existing conformance tests and validation rules to the selected diabetes scope, CMS122, PHA output, and participating source configurations | Intermediary / validation service | Months 2–4 |
| C. Technical and data deliverables | Existing technical architecture review and minor-update package | Reviews the existing architecture, data flows, environments, interfaces, and operational handoffs and documents only the modifications required for the pilot | Intermediary | Months 1–3 |
| C. Technical and data deliverables | Interface configuration and pilot enablement | Configures existing FHIR APIs, Bulk Data exports, scheduling, filters, authentication, routing, and PHA delivery for pilot use. It does not assume new source interfaces are built | HIT vendors, HCCN, and intermediary | Months 2–5 |
| C. Technical and data deliverables | HCCN consolidated-export configuration | Where the HCCN participates, configures or adjusts its existing aggregation services to produce one consolidated FQHC export | HCCN | Months 2–5 |
| C. Technical and data deliverables | Provider-panel attribution configuration and validation | Applies existing or available attribution data and logic to support the PHA output and CMS122 denominator | HCCN/providers and intermediary | Months 2–5 |
| C. Technical and data deliverables | Normalization, deduplication, and diabetes cohort logic updates | Reviews and makes limited changes to existing normalization, patient matching, deduplication, and cohort services to support the pilot’s diabetes definitions and outputs | Intermediary | Months 2–5 |
| C. Technical and data deliverables | Existing de-identification and aggregate-generation process configuration | Configures the intermediary’s existing privacy-transformation and aggregation services for the approved PHA outputs | Intermediary | Months 3–5 |
| C. Technical and data deliverables | Existing trust-layer configuration and diabetes-specific rule package | Configures the intermediary’s existing trust infrastructure for diabetes-specific conformance, completeness, timeliness, provenance, and audit measures | Intermediary | Months 2–5 |
| C. Technical and data deliverables | Trust scorecard and source-diagnostic updates | Adapts existing scorecards and source-specific diagnostics for the pilot’s diabetes elements, outputs, and remediation process | Intermediary | Baseline before go-live; updated during operations |
| C. Technical and data deliverables | Data-quality baseline and remediation package | Establishes an initial data-quality baseline and documents two targeted remediation cycles across the source configurations | Intermediary | Months 3–6 |
| C. Technical and data deliverables | CMS122 configuration and validation | Configures CMS122 using existing measure-execution capabilities or tools and validates denominator, numerator, exclusions, attribution, and output | Intermediary, with PHA validation | Months 3–6 |
| C. Technical and data deliverables | PHA surveillance output configuration | Configures the PHA’s existing analytics tool and intermediary transformations to produce diabetes prevalence, A1c testing, poor-control, and approved demographic/geographic stratifications | PHA analytics team | Months 3–6 |
| C. Technical and data deliverables | Automated PHA delivery configuration | Configures an existing secure delivery mechanism or makes limited modifications to deliver de-identified line-level and aggregate data to the PHA | Intermediary | Months 3–6 |
| C. Technical and data deliverables | Operational dual-use chronic dataset | Produces and operates the curated diabetes dataset using the existing intermediary platform and configured pilot logic | Intermediary | Initial production data product around Months 4–6; maintained during operations |
| C. Technical and data deliverables | Multi-use data demonstration | Demonstrates that one configured intake, processing, and trust pathway can support both the PHA output and CMS122 without building separate source pipelines | PHA and intermediary | During operations and evaluation |
| C. Technical and data deliverables | Operational monitoring and service-report configuration | Adapts existing intermediary monitoring to report data volumes, latency, interface status, processing errors, and SLA measures for the pilot | Intermediary | Before go-live and during operations |
| C. Technical and data deliverables | Optional UDS+ interface implementation | Creates or materially configures a UDS+ submission interface where no existing production pathway is available | HCCN and/or intermediary | Optional and separately priced |
| C. Technical and data deliverables | Optional chronic-referral data and analytic configuration | Uses an existing referral infrastructure and makes only limited data, workflow, and analytic changes needed to evaluate chronic-care referrals | Intermediary / existing referral platform | Optional and separately priced |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Integrated test plan | Covers unit, interface, conformance, data quality, security, measure, operational, and user-acceptance testing | Intermediary | Before test execution |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Baseline data-quality assessment | Initial conformance/completeness/timeliness assessment for each source configuration | Intermediary | Before go-live |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Remediation Cycle 1 | Corrects high-priority mapping, configuration, missingness, and processing defects | Vendors/providers/HCCN | Pre-go-live |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Remediation Cycle 2 | Re-tests corrections and addresses residual priority defects | Vendors/providers/HCCN | Pre-go-live or early operations |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Security and interface authorization-to-operate / connection approval | Approves pilot connections and environments for operation | PHA and intermediary security authorities | Before go-live |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Participant onboarding checklist and completion records | Tracks legal, technical, operational, support, and training readiness for each organization | Intermediary/HCCN | Months 2–6 |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Training materials and sessions | Covers source issue resolution, trust reports, PHA analytics, support, incident escalation, and operational responsibilities | Intermediary/HCCN/PHA | Before go-live and refreshers during operation |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Go-live readiness review | Formal gate confirming legal, technical, data, operational, and support readiness | PHA and intermediary | Before operational exchange |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | First successful operational data product | First accepted production-cycle dual-use dataset delivered to the PHA | Intermediary | Target Months 4–6 |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Nine-month live-exchange period | Operates incremental daily exchange of approximately 500–1,000 records per day | Intermediary | Target nine months; six-month sensitivity |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Operational SLA and data-quality reports | Recurring reports on volume, latency, failures, completeness, conformance, and remediation | Intermediary | Monthly or agreed cadence |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Pilot evaluation plan and baseline | Defines feasibility, implementation effort, data quality, reuse, utility, and scalability measures | PHA/site evaluation lead | Early pilot; baseline before build or go-live |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Interim evaluation findings | Assesses time-to-implement, quality improvement, reuse, and public health utility | PHA/site evaluator | Throughout operations |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Final site evaluation report | Summarizes feasibility, cost drivers, data quality changes, operational performance, utility, limitations, and scale implications | PHA/site evaluation lead | Last two months |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Implementation and onboarding playbook | Documents repeatable technical, governance, onboarding, remediation, support, and cost patterns | PHA and intermediary | Draft during operations; final at closeout |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | MENDS-informed readiness addendum | Describes readiness patterns informed by MENDS without making MENDS the operational backbone | PHA/intermediary | Closeout |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Transition and sustainability recommendations | Identifies options for continuing, scaling, funding, maintaining specifications, or terminating services | PHA and intermediary | Final two months |
| D. Testing, onboarding, training, operations, evaluation, and closeout products | Pilot closeout package | Completes final reporting, financial reconciliation, data disposition, access termination or transition, and lessons learned | PHA/project lead | End of Month 12 |

# 4. Cost-Estimating Approach

For this report, we prioritized official and primary sources in this order: HRSA and BPHC funding pages, CDC and CDC Stacks publications, ONC/ASTP funding and project pages, CMS and USAspending award summaries, APHL official program pages, official HIE pricing/FAQ pages, and official cloud-pricing documentation. I used academic implementation studies and vendor or sector writeups only when official sources did not expose a unit benchmark, and I label those uses as secondary. [6]

The most defensible default modeling stance for the base scenario is therefore this: treat governance/chartering as pre-pilot and unfunded; treat technical architecture, interfaces, normalization, deduplication, de-identification, and trust-layer functions as mostly existing; assume new funding primarily covers implementation planning, partner onboarding, source-specific mapping and remediation, trust/reporting adjustments, quality-measure output work, training, pilot operations, and evaluation; and model UDS+ and referral functions as explicit option switches rather than baked-in base scope. That posture is consistent with the pilot documents and with the strongest Analog evidence. [5]

The model uses low, base, and high estimating cases within each structural scenario. It treats participant counts, source configurations, interfaces, remediation cycles, operating months, evaluation intensity, labor rates, indirect-cost rates, and selected optional components as the principal adjustable quantities. Detailed work-breakdown and cost-build-up calculations remain model support rather than primary user-facing content.

# 5. Major Cost Drivers

The likely fixed-cost center for this pilot is central implementation and validation work: PM, intermediary adjustments, trust/data-quality reporting, quality-measure output logic, evaluation, and sponsor coordination. The largest variable-cost center is participant onboarding and remediation, especially if the sponsor funds any FQHC/HCCN effort directly. The most scale-sensitive variables are provider count, source-configuration count, UDS+ inclusion, and live-operations duration. The most schedule-sensitive items are remediation cycles, acceptance testing, and legal/privacy review. The categories most likely to be underestimated are source-data cleanup, participant in-kind time, and evaluation/dissemination. The items most likely to be contributed in kind are chartering, readiness attestations, vendor meetings, and source-system minor updates. The hardest areas to benchmark with public data are state-specific legal/privacy work and the true incremental cost of “lightweight” trust-layer changes on top of existing intermediary platforms. [52]

The following cost drivers and complexity factors were migrated from the workbook. They should be represented as editable assumptions, low/base/high conditions, sensitivities, or contingency risks in the cost model.

| ID | Cost driver or risk | Base position | High condition | Model treatment |
| --- | --- | --- | --- | --- |
| RD-01 | Intermediary operating model | Six scenarios modeled separately | Two layers or HCCN full-intermediary role requires added coordination/capability | Scenario selection |
| RD-02 | Broad longitudinal dataset scope | Narrow scope is base; broad work is incremental | Medication, follow-up, utilization, complication data require additional mappings or sources | Broad-scope increment |
| RD-03 | Production interface count and complexity | 3 interfaces with HCCN; 5 without | Additional unique endpoints, custom transport, or new relationship to intermediary | Editable quantity and high-case sensitivity |
| RD-04 | Existing architecture and platform reuse | Existing platforms and documentation require minor updates | Material gaps require new components or redesign | Base assumption plus contingency |
| RD-05 | HCCN ability to act as full intermediary | HCCN can ingest two non-FQHC providers and perform trust, measure, and delivery functions | Legal authority or technical capability is incomplete | Scenario-specific contingency |
| RD-06 | Data-quality thresholds and source variation | Feasibility-oriented thresholds; critical errors resolved | Strict thresholds or substantial missingness/local-code variation | Low/base/high complexity |
| RD-07 | Number of remediation cycles | Two cycles | Three or four cycles | Editable per-cycle input |
| RD-08 | Provider-panel attribution quality | Existing rosters require one reconciliation | Missing, inconsistent, or dynamic panels require manual cleanup | Complexity factor / allowance |
| RD-09 | Security authorization requirements | Standard connection/security reviews; no new ATO | Formal ATO, penetration test, or new security tooling required | Optional add-on or contingency |
| RD-10 | Agreement count and negotiation complexity | 3 primary agreements + 10 lightweight amendments | Unique negotiation, external counsel, or separate FQHC DUAs | Editable counts and complexity |
| RD-11 | Source mapping and vendor variation | Five source configurations; two shared FQHC patterns | Substantial local vocabulary and endpoint variation | Per-configuration low/base/high |
| RD-12 | CMS122 implementation platform and version | Existing measure engine; intermediary calculates and PHA validates | New engine, version gaps, or independent PHA calculation | Vendor quote / bounded component estimate |
| RD-13 | Nine months of operations within 12-month pilot | Approximately three months to go-live | Delays shorten operations or increase parallel staffing | Nine-month base; six-month sensitivity |
| RD-14 | Operational support intensity | Business-hours support with automated monitoring | Frequent failures, high ticket volume, or extended support coverage | Monthly run-rate low/base/high |
| RD-15 | Help-desk ticket volume | Low-to-moderate volume | Persistent source, access, or data-quality issues | Ticket-based sensitivity |
| RD-16 | PHA analytics capability | Existing analytics platform can be configured | New data mart, licenses, or dashboard development required | Contingency / vendor quote |
| RD-17 | Evaluation rigor and manual review sample | Formal pragmatic evaluation; targeted manual validation | Large manual chart review, independent evaluation, or extensive qualitative study | Editable evaluation input |
| RD-18 | Participant readiness and technical-assistance intensity | Participants selected for readiness; moderate TA | Readiness attestations prove inaccurate or staff capacity is limited | TA intensity range / contingency |
| RD-19 | Participant indirect-cost rates | Actual organization-specific rates | High negotiated indirect rates | Editable participant input |
| RD-20 | Existing licenses and environment capacity | Existing licenses and environments sufficient | New modules, environments, or capacity required | Optional add-on / vendor quote |
| RD-21 | Multi-party coordination burden | Monthly governance and biweekly implementation cadence | Turnover, unresolved authority, or frequent cross-party escalation | Monthly PM range |
| RD-22 | Training and staff turnover | Four cohorts and one refresher | Multiple cohorts, turnover, or repeated onboarding | Per-cohort sensitivity |
| RD-23 | Data disposition and closeout implementation | Charter defines retention and closeout decisions | Complex transition to ongoing operation or extended retention | Fixed closeout plus contingency |

# 6. Areas of Uncertainty and Estimate Limitations

The biggest unresolved issue is who pays for participant-side effort. Public HCCN and UDS+ sources prove that provider/network-side work is real and often substantial, but they do not tell us whether the Chronic Care Cascade sponsor will fund that work directly, expect the HCCN or HIE to absorb it, or expect participants to contribute it in kind. That decision has first-order consequences for the estimate because provider/network effort is one of the largest variable-cost pools in the public analogs. [48]

The next major uncertainty is how much of the “trust layer” is truly incremental. The pilot documentation and our assumptions say the trust layer, de-identification, and aggregate generation already exist in some form. Public advanced-FHIR and MENDS-validation benchmarks show that meaningful validation, conformance, and remediation work can still become expensive even when the platform exists. A conservative model should therefore avoid both extremes: not a zero-dollar placeholder, but not a net-new platform build either. [49]

Another material uncertainty is whether UDS+ is included. Public FY24 UDS+ award pages make this one of the clearest optional cost adders in the entire benchmark set. If the pilot includes UDS+, the model should carry a distinct participant-side add-on; if not, that line should be set to zero rather than hidden in generic provider support. [22]

Finally, public prices for legal/privacy/security work are sparse. There are good public scope analogs for governance, HIE policy, consent, and privacy-sensitive exchange, but very few official sources expose line-item budgets for state-specific data-use agreement drafting, privacy review, or security architecture review. That category is likely to be underestimated if it is treated as ordinary PM overhead. The safest modeling treatment is a contingency or explicit professional-services line with a low/base/high range. [50]

Additional model limitations carried forward from the workbook include provisional labor rates, unvalidated participant indirect-cost rates, pending confirmation of interface topology and participant readiness, and the assumption that required participant work is reimbursed rather than contributed as unreimbursed in-kind effort.

# 7. Risks and Potential Cost Impacts

The items below are the cost-model risks most likely to create a material step change, contingency draw, or schedule effect. The wording and validation actions are retained from the workbook.

| ID | Risk | Cost direction | Schedule direction | Validation needed |
| --- | --- | --- | --- | --- |
| RD-04 | Existing architecture and platform reuse | Potentially significant increase | High | Readiness validation and technical demonstration |
| RD-05 | HCCN ability to act as full intermediary | Significant increase or scenario invalidation | High | Validate HCCN authority, platform, staffing, and contracts |
| RD-07 | Number of remediation cycles | Linear increase | Moderate | Validate after baseline |
| RD-08 | Provider-panel attribution quality | Increase | Moderate | Assess panel data |
| RD-09 | Security authorization requirements | Significant increase | High | Confirm PHA/intermediary security requirements |
| RD-10 | Agreement count and negotiation complexity | Increase | High | Validate legal structure |
| RD-13 | Nine months of operations within 12-month pilot | Increase and/or reduced evidence | High | Validate detailed schedule and critical path |
| RD-14 | Operational support intensity | Recurring increase | Moderate | Define SLA and support model |
| RD-18 | Participant readiness and technical-assistance intensity | Increase | High | Validate at mobilization |
| RD-20 | Existing licenses and environment capacity | Increase recurring and one-time | Moderate | Inventory entitlements and environments |
| RD-21 | Multi-party coordination burden | Increase | High | Confirm governance cadence and roles |
| RD-23 | Data disposition and closeout implementation | Increase | Moderate | Confirm charter requirements |

# 8. Optional Components

The client-directed streamlined model retains four separately priced optional components. Other former add-ons—additional organizations, FQHCs, source configurations, interfaces, remediation cycles, operating duration, environment capacity, and technical-assistance intensity—are better treated as ordinary scale, schedule, or complexity inputs within the base model.

| ID | Optional component | Trigger | Applies to | Key cost driver |
| --- | --- | --- | --- | --- |
| ADD-01 | UDS+ interface | Charter includes UDS+ and no adequate existing pathway is available | Any scenario | May require a new interface, mapping, authentication, and HRSA validation |
| ADD-02 | Closed-loop chronic-care referral analysis | Charter includes referral add-on and an existing referral platform/governance model is operational | Any scenario with existing referral infrastructure | Marginal workflow, data, and evaluation configuration only |
| ADD-03 | New medication-dispensing connection | Broad scope requires dispensing data not already available | Broad-scope scenarios if existing data are unavailable | New pharmacy/payer interface and data-use work |
| ADD-10 | Formal security authorization or penetration testing | PHA/intermediary requires ATO-equivalent approval, independent assessment, or new control documentation | Any scenario | Formal security authorization, independent assessment, penetration testing, or new control documentation |

# 9. Cross-Use-Case Applicability

The cost model’s management, governance, legal/privacy/security, specification, configuration, testing, onboarding, operations, evaluation, and closeout structure is generally portable to other HDU pilots. Use-case-specific adaptation is required for the minimum dataset, source systems, standards and implementation guides, specialized subject-matter expertise, technical transformation or linkage logic, outputs, and evaluation measures. This report does not re-estimate the other pilots or introduce new benchmark findings.

# 10. Benchmark Summary

The highest-value sources for continuing Stage 2 modeling are, in order, the HRSA HCCN pages, CDC MENDS articles, ONC LEAP pages, CMS PCG-FHIR and eCQI artifacts, APHL AIMS infrastructure pages, and official HIE fee schedules. Those are the sources that most directly convert pilot language into benchmarkable work and public dollar signals. Secondary academic implementation studies are still useful, but mainly for hours and effort ranges, not for sponsor-grade budget authority. [51]

# Appendix A. Whole-Project Analog Awards

| Analog | Total public value | Period of performance | Scope and deliverables most relevant to pilot | Why it matters for the pilot | Key caveats | Source |
| --- | --- | --- | --- | --- | --- | --- |
| HRSA FY25 HCCN Cooperative Agreements | ~$48M across 49 HCCNs | Aug. 1, 2025 – Jul. 31, 2028 | HCCNs must support at least 10 participating health centers and focus on data management/analytics, interoperability and data sharing, and UDS+ implementation. Required activities include customized data support, governance frameworks, FHIR-based reporting, feedback to EHR vendors, and readiness work. | Closest official Analog for the FQHC/HCCN portion of the pilot. Implies about $326.5k per HCCN-year on average before adjusting for local scale. | Broad national program, not a one-site pilot; includes activities wider than the narrow A1c base case. | [8] |
| Minnesota FY19 HCCN award example | $520,000 | Award year 2019; detail page does not state exact POP | Support for 10 participating health centers through Neighborhood Health Care Network. | Useful participant-level proxy for a smaller HCCN footprint; implies about $52k per participating health center in this award example. | Older award; page does not expose exact budget period or line-item scope. | [9] |
| Colorado FY19 HCCN award example | $650,000 | Award year 2019; detail page does not state exact POP | Support for 19 participating health centers through Colorado Community Managed Care Network. | Useful participant-level proxy for a somewhat larger network; implies about $34.2k per participating health center in this award example. | Older award; scope not line-item detailed on the public page. | [10] |
| HRSA ARP 2021 HCCN awards | $10,562,161 across 49 HCCNs | One-time ARP supplement; detailed national award page published 2021 | One-time readiness and modernization infusion to HCCNs; OCHIN received $682,500, AllianceChicago $357,500, New York HCCNs $292,500–$390,000, etc. | Good benchmark for one-time network readiness funding, averaging about $215.6k per HCCN nationally. | Emergency-era supplement; not a full operating program. | [11] |
| CDC MENDS program model | Official total value not stated in the 2023 CDC Stacks article; program described as CDC-funded | Reported in 2023 article; implementation reflected site work through 2023 | Five partner sites, 91 health-system/clinic partners, ~10 million patients; implementation areas included governance, partnerships, technical infrastructure/support, chronic-disease algorithms and validation, weighting/modeling, and workforce education. | Strong conceptual and operational Analog for chronic-disease surveillance through distributed EHR contributors and intermediary-style partners. | Official article does not state a total program value; useful mainly for scope and structure. | [12] |
| CDC MENDS validation award | $1.8M | Validation analysis covered Dec. 2020 – Aug. 2023 | Validation process across five data-contributing organizations; explicit focus on completeness, duplicate/missing records, mapping issues, implausible values, and remediation. | Strong Analog for the pilot’s trust-layer and remediation effort; if evenly allocated, roughly $360k per contributor/site. | This is validation-focused, not full pilot operations; the exact relationship to broader MENDS funding is not fully transparent in public sources. | [13] |
| ONC LEAP 2023 awards | $2M across 2 awards | Projects from 2023–2025 and 2023–2025/2026 | One HIE-centered advanced FHIR pilot and one FHIR data-quality platform pilot for USCDI using open-source tooling. ONC FAQ indicates areas 1 and 2 awards were capped at $1M total over two years. | Excellent benchmark for “advanced FHIR but limited-site” work and for trust/data-quality platform increments. | These are innovation awards, not service-delivery pilots; they can overstate cost if your pilot mostly reuses existing assets. | [14] |
| ONC LEAP 2020 awards | Up to $2.5M across 3 awards | Two-year awards under 2020 NOFO | Supported development and testing of modern API-based data-sharing functionality for registry and research use cases; ONC FAQ states areas 1 and 2 were up to $1M and area 3 up to $500k over two years. | Useful upper-mid benchmark for “new standards functionality plus implementation/testing” work. | Broader development orientation than this pilot; exact per-award values not located in an official project page. | [15] |
| APHL AIMS+ NIH OTC reporting contract | Up to $8.8M over 3 years | 2022–2025 | Centralized electronic results reporting from OTC manufacturers to local, state, and federal PHAs through AIMS+. | Strong Analog for centrally managed public-health intermediary exchange and national routing/orchestration. | National and infectious-disease focused; much larger scale than the base scenario. | [16] |
| CMS PCG-FHIR contract | $4.3316M | Nov. 30, 2023 – Nov. 30, 2025 | FHIR endpoint/service used as an API-based communication channel between providers and CMS; CMS privacy documentation says it receives structured and unstructured FHIR submissions and converts them to legacy formats for CMS workflows. | Good federal benchmark for operating and enhancing a managed FHIR service with compliance and transformation requirements. | Not public-health surveillance; federal-grade support stack can overstate a one-site state pilot. | [17] |
| VA–HealthInfoNet HIE contract | $360k obligated; $1.083M potential | Apr. 1, 2025 – Dec. 31, 2029 | Purchase of HIE services from a state/regional HIE for VA operations. | Useful recurring-service Analog for a subscription-style HIE relationship rather than a build. | Much lighter scope than a full public-health analytic pilot. | [18] |
| CDC state chronic disease surveillance NOFO example | Average award ~$575k; floor $500k; ceiling $650k | Year-1 project period beginning Jun. 30, 2021 in cited FAQ | State-site chronic disease surveillance funding benchmark. | Useful lower-bound public-health site Analog for PHA-side programmatic effort. | Not specifically interoperability-focused; less useful for intermediary and provider-side engineering. | [19] |

# Appendix B. Component-Level Benchmarks

| Component | Public benchmark | Unit | What it likely covers | What it likely does not cover | Modeling use | Source and confidence |
| --- | --- | --- | --- | --- | --- | --- |
| Average HCCN operating support | $326,531 | per HCCN-year | Network staff, TA, analytics, interoperability support, UDS+ activities across multiple PHCs | Site-specific custom development, heavy intermediary build, state-PHA analytics | Good top-down benchmark for the HCCN portion of the base scenario | High; official HRSA program + calculation. [20] |
| Participant-level HCCN support | $34,211–$52,000 | per participating health center in FY19 examples | Network coordination and support intensity by PHC count | May bundle broader network overhead | Useful per-FQHC proxy | Moderate; official award pages, older program year. [21] |
| One-time HCCN readiness infusion | $215,554 average | per HCCN one-time average | Readiness and short-term modernization surge | Multi-year operations | Good benchmark for a one-time participant enablement line | High; official HRSA ARP award page + calculation. [11] |
| UDS+ add-on for health centers | Sampled $31,398–$82,794; most sampled awards clustered ~$32k–$52k | per health center | Direct UDS+ supplement to active H80 grantee | HCCN network operations; broader pilot functions | Best public benchmark if the pilot includes UDS+ | Moderate; official state award pages, sampled not nationwide. [22] |
| Advanced FHIR or trust-layer project increment | Up to ~$1M over 2 years | per ONC LEAP award | Advanced FHIR capabilities, open-source tooling, piloting, testing, dissemination | Routine local operations using preexisting infrastructure | Upper-bound benchmark for nontrivial trust/data-quality/FHIR enhancement work | High for cap, moderate for applicability. [14] |
| Governance-development Analog | $200k–$400k per award | per cooperative agreement award | Interoperability policy, business practices, governance criteria, reducing exchange cost/complexity | Heavy technical implementation | Useful for sponsor-funded governance facilitation if charter work were funded | Moderate; official Grants.gov opportunity exposes floor/ceiling, not actual awards. [23] |
| Managed FHIR service operations | $180,484/month | monthly contract burn implied by CMS PCG-FHIR | Operate, maintain, enhance FHIR server/service with compliance transformation work | Provider-side onboarding, state PHA use cases | High-side recurring O&M comparator | High for contract total, moderate for fit. [17] |
| HIE subscription service | $6,316/month base; $19,005/month potential | monthly | Recurring HIE service relationship | New data product build and evaluation | Lower recurring managed-service comparator | High for contract amounts, moderate for fit. [18] |
| Per-clinician exchange participation fee | $450/year | per clinician-year | Ambulatory provider acting as recipient, supplier, or both in NCHIIN | Project PM, analytics, modernization | Useful if intermediary charges participant fees or if sponsor offsets them | Moderate; official HIE fee page. [24] |
| Per-result delivery fee | $0.06/result | per lab/radiology/document result delivered | High-volume hospital/lab result exchange | Analytics, trust layer, governance | Useful for variable transaction-cost sensitivity testing | Moderate; official HIE fee page. [24] |
| Annual interface maintenance ratio | 20% of interface development cost | annual % of original development | Ongoing interface maintenance after year one | Original build/configuration cost | Useful rule of thumb for post-pilot recurring maintenance | Moderate; official HIE fee page. [24] |
| Operational support plan | $145–$400/month or $85/hour ad hoc | per org-month or per support hour | Help desk, maintenance, upgrades, workflow support | Formal project implementation | Useful for ongoing support/help-desk line | Moderate; official NCHIIN support page. [25] |
| Zero-fee HIE participation comparator | $0 subscription fees for physicians/medical groups | per participant | No-charge physician participation in Manifest MedEx | Back-end subsidization not visible publicly | Valuable lower-bound comparator showing some ecosystems socialize exchange cost | Moderate; official/official-partner FAQ pages. [26] |
| Straightforward FHIR setup using existing endpoint | 4–40 hours | setup hours per site | Standards-based configuration where FHIR access already exists | Complex local data model remediation | Good low/base setup-effort benchmark consistent with the pilot’s reuse assumption | Moderate; peer-reviewed implementation study, secondary. [27] |
| Complex logic/phenotype implementation | 200–250 hours first site; ~20 hours reused in same Epic environment | hours per implementation | First-instance algorithm implementation on unseen EHR data; much lower with reuse | Broader governance/evaluation | Best public proxy for CMS122-style custom logic or cohort/transformation effort | Moderate; peer-reviewed study, secondary. [28] |
| Local reporting setup and upkeep | 40–80 initial hours; 1–2 hours/month ongoing per site | hours | Report creation and routine refresh/maintenance | Full FHIR pipeline creation | Useful for surveillance or dashboard output configuration | Moderate; AHRQ PSNet implementation report, secondary but credible. [29] |
| Large-scale FHIR refresh processing time | ~39 hours import; ~80 hours export/import for 3.24M-patient cohort | elapsed processing time per full refresh | Bulk import/export and transformation steps | Labor cost directly | Useful for sizing orchestration windows and compute, not for direct labor pricing | Moderate; MENDS-on-FHIR peer-reviewed article, secondary. [30] |
| Cloud storage benchmark | $0.0208/GB-month hot storage; $0.055 per 10,000 writes; $0.0044 per 10,000 reads | cloud unit pricing | Commodity storage and basic transactions | Engineering labor, support, data governance | Confirms that modest pilot cloud storage is usually a minor line item | High for unit prices, moderate for scenario fit. [31] |
| Cloud logging benchmark | $0.50/GB initial ingestion for CloudWatch Lambda logs; destination delivery from $0.25/GB | per GB | Logging/monitoring ingest | App engineering and incident response | Ceiling-style monitor/log estimate for observability | Moderate; official AWS sources. [32] |
| National-scale public-health exchange cloud optimization | ~$258,000/month savings | monthly savings | Effect of architectural tuning at very high national messaging scale | Small-site pilot hosting | Strong evidence that cloud cost matters mainly at very large scale | Moderate; official APHL operations article. [33] |
| Relevant quality-measure spec | CMS122FHIR active for 2026 | measure artifact | FHIR digital quality measure for diabetes glycemic status >9%; part of APP and APP Plus ecosystems | Effort hours or dollars | Confirms measure relevance, not cost | High; official eCQI pages. [34] |

# Appendix C. Mapping to the Cost Model and Recommended Defaults

| Stage 1 cost driver or WBS item | Most relevant benchmark(s) | Mapping logic |  | Recommended modeling treatment |  |
| --- | --- | --- | --- | --- | --- |
| Participant funding for HCCN/FQHC network enablement | HRSA FY25 HCCN average; FY19 MN/CO HCCN examples | Closest proxy for network-side coordination, analytics, interoperability, and UDS+ support across FQHC participants |  | Use as a variable per FQHC-equivalent benchmark, not as a flat site fee. [35] |  |
| One-time participant readiness | HRSA ARP 2021 HCCN awards | Best proxy for “readiness surge” rather than multi-year steady-state support |  | Use as a one-time optional participant-enablement parameter. [36] |  |
| Optional UDS+ increment | FY24 QIA-UDS+ state award pages | Directly analogous to health-center work for patient-level UDS+ submission |  | Model as an explicit add-on switch per participating health center. [22] |  |
| Intermediary trust-layer and data-quality updates | ONC LEAP 2023 FHIR data-quality project; CDC MENDS validation award | These sources bound the cost of meaningful data-quality and trust work beyond trivial scripting |  | Use a small-share-of-LEAP-class project assumption for reused infrastructure; use MENDS validation as a caution against underbudgeting remediation. [37] |  |
| Source mapping and remediation cycles | REDCap FHIR setup hours; phenotype implementation hours; MENDS validation findings | Straightforward reused-source setup can be short; first-instance logic or poor-quality source mappings can be much larger |  | Model with a low/base/high hour range per source configuration, not a single average. [38] |  |
| Quality-measure logic and A1c output | CMS122FHIR spec; phenotype logic hours; report setup hours | Measure artifact is official; implementation effort is best proxied by phenotype/reuse studies and report-setup literature |  | Separate measure logic setup from recurring report execution. [39] |  |
| Recurring support/help desk | NCHIIN support plans and ad hoc hourly support | Publicly posted support-plan pricing is a good proxy for steady-state pilot support |  | Model as either per org-month or pooled support hours. [25] |  |
| Recurring interface maintenance | NCHIIN 20% annual maintenance rule | Best public rule-of-thumb for post-year-one ongoing interface cost |  | Use as a recurring maintenance ratio only if the pilot creates or materially upgrades interfaces. [24] |  |
| Subscription-style managed exchange service | HealthInfoNet contract; Manifest MedEx no-fee comparator | Shows that market models range from subsidized/free-to-participant to measurable managed-service subscriptions |  | Keep as a scenario toggle depending on who absorbs intermediary cost. [40] |  |
| Cloud and observability | Azure storage/pricing; AWS logging; APHL AIMS savings | Unit prices are low at pilot scale, but national systems can realize very large savings from optimization |  | Treat as a minor base-case line item with an upside sensitivity only if volume or logging explodes. [41] |  |
| Governance and legal facilitation | ONC Exemplar HIE Governance award range | Useful only if sponsor funds charter support or external facilitation; otherwise Stage 1 assumption is this work is pre-pilot and unfunded |  | Default to out-of-scope for sponsor estimate unless the charter assumption changes. [23] |  |
| Evaluation and dissemination | MENDS and LEAP publications; APHL and ONC projects | Public analogs consistently include lessons learned, evaluation, and dissemination outputs even where cost lines are not separable |  | Keep as a distinct WBS item; do not bury in PM or TA. [42] |  |
| Parameter for cost model | Recommended default | Conservative range | Rationale |  | Confidence |
| Net-new source interfaces in base scenario | 0 | 0–1 | Stage 1 working assumption is that most interfaces already exist and only minor updates are expected; the benchmark literature supports much lower setup effort when standards endpoints already exist. [43] |  | Moderate |
| Source configurations requiring material mapping/remediation | 5 | 5–7 | User-specified base scenario is 5 source configurations; MENDS shows each contributor can surface distinct remediation needs. [44] |  | High |
| Minor setup/configuration effort per straightforward source | 20–40 hours | 4–40 hours | Matches published experience where FHIR-based setup exists and scope is constrained. [27] |  | Moderate |
| Complex first-site mapping or logic effort | 200 hours | 200–250 hours | Conservative default for one difficult source or custom logic stream, based on published first-site phenotype implementation. [28] |  | Moderate |
| Reuse discount for same-EHR implementation | ~20 hours | 20–40 hours | Published reuse case suggests major savings once the logic is already built for the same EHR family. [28] |  | Moderate |
| HCCN/FQHC support benchmark | Use $35k–$40k per FQHC-equivalent as a base modeling placeholder | $34k–$52k | Anchored in FY19 HCCN network examples and slightly conservative relative to the broader FY25 national HCCN average. This is a benchmark input, not a recommended payment policy. [45] |  | Moderate |
| UDS+ add-on if included | $40k per participating health center | $32k–$62k typical; high-case $83k | Directly anchored in FY24 QIA-UDS+ awards sampled from multiple states. [22] |  | Moderate |
| Trust/data-quality update line | 10%–20% of a LEAP-class 2-year project equivalent | roughly one-tenth to one-quarter of $1M | Because the pilot assumes these capabilities already exist, a full $1M advanced-FHIR/data-quality build would overstate the base case; still, MENDS validation evidence argues against setting this to zero. [46] |  | Low to moderate |
| Recurring support model | Centralized light support plus pooled ad hoc hours | $145–$225 per org-month equivalent or $85/hour | Public HIE support-plan pricing is more realistic than assuming no support. [25] |  | Moderate |
| Recurring interface maintenance after pilot year one | 20% of original interface-development cost | 15%–25% | Direct published maintenance rule from NCHIIN. Use only where the pilot materially changes an interface. [24] |  | Moderate |
| Cloud storage cost | Treat as minor | Use published unit rates, but keep as a low-share line | Official storage and request rates are small relative to labor for a modest one-site pilot. [47] |  | High |
| Governance/charter facilitation in sponsor estimate | Exclude from funded pilot unless assumption changes | Include only if later funded | Your Stage 1 instruction was that chartering occurs before the pilot and is not funded. Official governance benchmarks are still useful as a sensitivity case if that changes. [23] |  | High |

# Appendix D. Prioritized Sources and Links

HRSA FY25 HCCN Cooperative Agreements — closest official whole-project Analog for HCCN-enabled analytics, interoperability, and UDS+. [53]

HRSA FY25 HCCN Objectives and Sample Activities — maps directly to data management, interoperability, QHIN, FHIR reporting, and UDS+ work. [54]

CDC MENDS 2023 article — strongest official scope description for chronic-disease surveillance via distributed EHR contributors and intermediary partners. [12]

CDC MENDS validation article — best official source on trust, validation, remediation, and related award amount. [44]

ONC LEAP 2023 projects and award notice — strongest official benchmark for advanced FHIR and FHIR data-quality pilot scale. [55]

APHL AIMS platform and OTC-reporting contract — best official intermediary/public-health exchange service Analog. [56]

CMS PCG-FHIR contract and PIA — official benchmark for managed FHIR endpoint operations and transformation/compliance scope. [57]

NCHIIN fee and support pages — practical public pricing for per-clinician fees, per-result fees, maintenance ratio, help desk, and support plans. [58]

Manifest MedEx participation FAQ — useful zero-fee comparator for subsidized HIE participation economics. [26]

Official cloud-pricing pages — good for keeping cloud as a bounded, usually minor line item. [47]

eCQI CMS122FHIR pages — confirms the A1c/digital-measure target and its current FHIR representation. [59]

Secondary academic effort benchmarks — best available public hours for existing-endpoint FHIR setup, reuse discounts, and complex first-site mapping. [60]

[1] [2] [5] [6] [7] [8] [20] [35] [48] [51] [53] https://bphc.hrsa.gov/funding/funding-opportunities/health-center-controlled-networks-hccn

[3] [12] [42] https://stacks.cdc.gov/view/cdc/124328

[4] [27] [38] [43] [60] https://pmc.ncbi.nlm.nih.gov/articles/PMC12494410/

[9] https://bphc.hrsa.gov/funding/funding-opportunities/health-center-controlled-networks-hccn/fy19-awards/mn

[10] [21] [45] https://bphc.hrsa.gov/funding/funding-opportunities/health-center-controlled-networks-hccn/fy19-awards/co

[11] [36] https://bphc.hrsa.gov/funding/funding-opportunities/health-center-controlled-networks-hccn/fy2021-awards

[13] [44] [49] [52] https://www.cdc.gov/Pcd/issues/2024/23_0409.htm

[14] [37] [46] [55] https://healthit.gov/interoperability/investments/leap/2023-leap-health-it-projects/

[15] https://healthit.gov/news/leading-edge-acceleration-projects-leap-health-information-technology-health-it/

[16] [56] https://aphl.org/news/newsroom/press-release/aphl-awarded-nih-contract-for-reporting-otc-covid-19-results-to-public-health-agencies

[17] [57] https://www.usaspending.gov/award/CONT_AWD_75FCMC24F0014_7530_47QTCA21D004Y_4732

[18] [40] https://www.usaspending.gov/award/CONT_AWD_36C24125P0135_3600_-NONE-_-NONE-/

[19] https://archive.cdc.gov/www_cdc_gov/dhdsp/programs/pcnasr_foa.htm

[22] https://bphc.hrsa.gov/funding/funding-opportunities/quality-improvement-fund-uds-system-patient-level-submission/awards/mn

[23] [50] https://simpler.grants.gov/opportunity/71658cc0-fd17-45dd-a0e4-a78e02c8eb59

[24] [58] https://www.nchiin.org/health-information-exchange/

[25] https://www.nchiin.org/network-services/

[26] https://iehio.org/providers/faq/

[28] https://pmc.ncbi.nlm.nih.gov/articles/PMC11629037/

[29] https://psnet.ahrq.gov/innovation/suicide-prevention-emergency-department-population-ed-safe

[30] https://pmc.ncbi.nlm.nih.gov/articles/PMC10690355/

[31] [41] [47] https://learn.microsoft.com/en-us/azure/storage/blobs/blob-storage-estimate-costs

[32] https://aws.amazon.com/blogs/compute/aws-lambda-introduces-tiered-pricing-for-amazon-cloudwatch-logs-and-additional-logging-destinations/

[33] https://aphl.org/our-publications/stories/lab-matters-magazine/article/spring-2026/managing-sustainable-public-health-data-exchange-at-the-national-level

[34] [39] [59] https://ecqi.healthit.gov/sites/default/files/ecqm/measures/CMS122FHIR-v1.0.000-FHIR.html

[54] https://bphc.hrsa.gov/funding/funding-opportunities/health-center-controlled-networks-hccn/objectives-sample-activities