## Sheet1
ID | Priority | Input Required | What You Need to Provide | Suggested Options or Current Working Assumption | Your Response
S01 | Required | Pilot condition domain | Name the single chronic condition addressed by this pilot | Hypertension; diabetes; childhood asthma; another defined domain | Diabetes
S02 | Required | Primary measure or analytic workflow | Identify the one measure, surveillance indicator, or workflow that will be fully operational | Example: hypertension control; diabetes care cascade; asthma-related acute-care utilization | Diabetes care cascade
S03 | Required | Primary customer | Identify the organization or program expected to use the operational output | Participating STLT chronic disease program | Participating STLT chronic disease program
S04 | Required | Primary operational output | Describe exactly what will be delivered to the primary customer | Line-level dataset; aggregate dataset; recurring extract; FHIR resource set; measure result; analytic table | Intermediary (HIE/HDU) supplied dashboard with drilldown to patient level
S05 | Required | Primary output cadence | State how frequently the operational output will be produced | Near real time; daily; weekly; monthly; quarterly | Near real time
S06 | Required | Primary output access method | State how the recipient receives or accesses the output | Existing portal; secure file transfer; API; Bulk FHIR; direct database access; existing BI tool | Existing portal
S07 | Required | Primary output data-access level | State the level of detail delivered | Identifiable line-level; limited dataset; de-identified line-level; aggregate | Identifiable line level
S08 | Required | Secondary downstream use | Identify the second reuse to be demonstrated | HRSA-aligned output; NCQA/digital quality result; CDC program extract; other | HRSA-aligned output
S09 | Required | Secondary-use artifact | Define what constitutes completion of the second reuse | One-time measure calculation; FHIR MeasureReport; sample extract; validated transformation; recurring nonproduction output | UDS+ FHIR bundle
S10 | Required | Secondary-use boundary | Confirm that it is a demonstration rather than a second production implementation | Working assumption: no new production interface, SLA, dashboard, or recurring support | No new production interface, SLA, dashboard, or recurring support
S11 | Required | Exchange-period requirement | Select the required production exchange period | Minimum six months; target nine months; firm nine months | Minimum six months; target nine months
S12 | Required | Exchange-period start rule | Define when the exchange clock begins | When minimum operational cohort and primary output are live | Minimum operational cohort live
S13 | Required | Minimum operational cohort | State how many provider networks must be live before the exchange period begins | Recommended: four of six | Four
S14 | Required | Final participation target | Confirm the total number of provider networks expected to participate | Current assumption: six | Six
S15 | Required | Rolling onboarding permitted | Confirm whether remaining networks may join after the exchange period begins | Recommended: yes, during a defined early ramp-up period | Yes
S16 | Required | Ramp-up window | Specify how long remaining sources have to join after initial go-live | One month; two months; no rolling onboarding | One month
S17 | Required | Total project duration | Confirm the period from mobilization through closeout | Current assumption: 12 months | 12 months
S18 | Required | Pre-award work permitted | Identify which activities may occur before the formal 12-month pilot begins | Participant selection, readiness review, use-case selection, draft dataset, legal-path assessment | Participant selection, readiness review, use-case selection, draft dataset, legal-path assessment
P01 | Required | Intermediaries per pilot | Confirm the number of intermediary organizations | Current assumption: one | One
P02 | Required | STLT jurisdictions per pilot | Confirm the number of participating jurisdictions | Current assumption: one | One
P03 | Required | Named or representative intermediary | Identify the actual intermediary, if known, or the type to model | State HDU; statewide HIE; regional HIE; HCCN; other | State HDU or statewide HIE
P04 | Required | Named or representative STLT | Identify the actual jurisdiction, if known, or describe the model jurisdiction | State health department; territorial agency; local health department | State Health Department
P05 | Preferred | Provider-network identities | List the six expected networks, if known | Names or representative provider types | FQHC, CCBHC, Endocrinology Clinic, Pharmacy, Community-Based Hospital System
P06 | Required | Provider-network composition | Describe what counts as one provider network | Health system; HCCN; FQHC network; ACO; hospital network; other | HCCN; Hospital Network
P07 | Required | Distinct EHR vendor count | Estimate the number of different EHR products represented across the six networks | 1–2; 3–4; 5–6; unknown | Three
P08 | Required | Distinct EHR instance count | Estimate the number of separately configured EHR instances | Number or range | Five
P09 | Required | Other source-system count | Identify non-EHR sources required for the base pilot | None; laboratory; claims; pharmacy; ADT; registry; other | Laboratory; claims; pharmacy; ADT
P10 | Required | Connectivity threshold | Confirm the minimum percentage of required source pathways already connected | Current assumption: at least 75% | At least 75%
P11 | Required | Meaning of “connected” | Confirm the readiness definition | Recommended: production feed exists, required data are present, and reuse is legally permitted | Production feed exists, required data are present, and reuse is legally permitted
P12 | Required | New endpoint cap | Confirm the maximum number of materially new endpoint configurations | Current assumption: no more than two; for nine months, preferably zero or one | Two or less
P13 | Required | Treatment if cap is exceeded | State what happens if readiness shows more new endpoints are required | Remove source; reduce cohort; separately fund; abandon participant; revise budget | Remove source
P14 | Preferred | Backup participants | State whether backup provider networks will be identified before award | Yes or no | Yes
D01 | Required | Minimum dataset size | Confirm the intended size or provide the draft data-element list | Current planning range: approximately 15–25 elements | 20-25 Elements
D02 | Required | Required stratifications | Identify required demographic or geographic stratifications | Age; sex; race/ethnicity; geography; payer; organization; other | Age; sex; race/ethnicity; geography; payer; organization
D03 | Required | Required provenance fields | Identify minimum source and transformation metadata | Source organization, source system, timestamps, transformation history | Source organization, source system, timestamps, transformation history
D04 | Required | Data sources permitted | Identify which formats or pathways may support the base use case | FHIR API; Bulk FHIR; HL7 v2; C-CDA; flat file; existing repository | FHIR API; Bulk FHIR; HL7 v2; C-CDA
D05 | Required | Preferred technical pathway | Select the primary pathway the pro forma should model | Existing intermediary repository; Bulk FHIR; REST API; existing HL7 feeds; mixed | Mixed: existing intermediary repository, Bulk FHIR, existing HL7 feeds
D06 | Required | Measure specification source | Identify the authoritative clinical or measure specification | CDC definition; CMS measure; HRSA UDS+ measure; NCQA measure; locally defined logic | CMS measure
D07 | Required | Measure licensing | State whether the selected measure requires licensing | Yes; no; unknown | No
D08 | Required | Measure engine availability | State whether the intermediary already has an appropriate execution engine | Existing CQL engine; other analytics engine; no engine required; unknown | Existing engine
D09 | Required | Patient matching requirement | Define whether the use case requires longitudinal matching | Existing MPI only; cohort attribution without matching; no matching; other | Existing MPI
D10 | Required | Existing MPI adequacy | Confirm whether the intermediary’s current matching capability is assumed sufficient | Current assumption: yes; no new MPI development | Yes
T01 | Required | Existing hosting | Confirm that the intermediary will use an existing hosted environment | Current assumption: yes | Yes
T02 | Required | Existing IAM | Confirm existing identity and access management will be reused | Current assumption: yes | Yes
T03 | Required | Existing audit and logging | Confirm existing logging and audit capabilities will be reused | Current assumption: yes | Yes
T04 | Required | Existing operations support | Confirm that production monitoring, incident management, and help desk already exist | Current assumption: yes | Yes
T05 | Required | Existing development and test environments | Confirm whether these environments are already available | Yes; no; partially | Yes
T06 | Required | Existing data-normalization capability | Confirm whether the intermediary already normalizes relevant data | Yes; no; partially | Yes
T07 | Required | Custom application development | Confirm exclusion of custom portal or dashboard development | Current assumption: excluded | Excluded
T08 | Required | Standard report format | Select what replaces a custom dashboard | Existing dashboard; CSV/Excel extract; PDF quality report; API response; BI dataset | Existing dashboard and/or CSV/Excel extract
T09 | Preferred | Estimated data volume | Provide approximate patients, encounters, records, or transactions per month | Number or range | 324,772 to 3,539,000 patients
T10 | Preferred | Number of environments charged to pilot | State whether the pilot pays incremental costs for development, test, and production | Existing/included; incremental; unknown | Existing/included
G01 | Required | Legal pathway | Describe the expected agreement approach | Existing DUA covers use; addendum required; new DUA; multiple provider agreements; unknown | Existing DUA covers use or addendum required
G02 | Required | Number of expected agreements | Estimate the number of agreements or addenda | One statewide agreement; one per provider; other | One intermediary agreement will cover it
G03 | Required | Federal data-access requirement | State whether CDC will directly receive pilot data | Yes—line-level; yes—de-identified; yes—aggregate; no direct data access | No direct data access
G04 | Required | Secondary-consumer agreement | State whether the secondary use requires a distinct data-sharing agreement | Yes; no; unknown | Yes
G05 | Required | Security approval pathway | Identify who must approve the intermediary’s controls | Intermediary only; STLT; provider networks; CDC; another entity | STLT
G06 | Required | CDC ATO assumption | Confirm whether a CDC authorization to operate is required | Current assumption: no CDC ATO unless CDC-hosted | No CDC ATO required
G07 | Required | Consent requirement | State whether individual consent is expected to apply | No; yes; unknown | Uknown
G08 | Required | Data-retention requirement | Define how long pilot data must be retained | Existing policy; pilot duration only; defined number of years; unknown | Existing policy
G09 | Preferred | Redisclosure restrictions | Identify any known downstream-use restrictions | Description or unknown | Unknown
F01 | Required | STLT funding treatment | Select how STLT work will be funded | Direct award; subaward; fixed stipend; reimbursed labor; in kind | Direct award and subaward
F02 | Required | Intermediary funding treatment | Select how intermediary work will be funded | Fixed subaward; cost-reimbursement; milestone payments; prime subcontract | Subaward
F03 | Required | Provider funding treatment | Select whether provider effort will be compensated | In kind; fixed stipend; reimbursed labor; paid through intermediary | In kind or reimbursed labor
F04 | Required | Provider stipend amount or method | If providers are compensated, specify the amount or calculation basis | Fixed per network; actual labor; capped allowance; TBD | Capped allowance
F05 | Required | Vendor-fee funding | State who pays EHR or vendor implementation charges | Sponsor; intermediary; provider; shared; excluded | Excluded
F06 | Required | Legal-cost funding | State whether participant legal costs are reimbursable | Yes; no; allowance only | No
F07 | Required | Security-review funding | State whether participant security review is reimbursable | Yes; no; allowance only | No
F08 | Required | In-kind valuation | State whether Stage 4 should monetize participant in-kind labor | Yes; report hours only; both hours and value; exclude with disclosure | Report hours only
F09 | Required | Existing infrastructure treatment | Select how existing HDU infrastructure should be represented | Exclude from sponsor cost but report as contributed value; do not monetize; allocate estimated value | Do not monetize
F10 | Required | Sponsor-funded cost target | Confirm the target for each direct pilot budget | Current target: approximately $3 million | $3 million
F11 | Required | Treatment of shared portfolio costs | Select reporting method | Central only; allocated equally; allocated by labor usage; show both central and allocated views | Central only
F12 | Required | Portfolio size | Confirm how many pilots will share common assets | Three; four; another number | Up to four
F13 | Required | Contingency treatment | Select how contingency should be modeled | Fixed percentage; risk-item allowances; both; no contingency | Fixed percentage
F14 | Preferred | Target contingency level | Provide target percentage or leave for Stage 4 recommendation | Example: 5%–10% | Recommend in STAGE 4
Q01 | Required | Testing rigor | Define the expected testing level | Basic conformance and end-to-end; formal parallel comparison; extensive edge cases | Basic conformance and end-to-end
Q02 | Required | Remediation-cycle definition | Confirm whether the two-cycle cap applies per source pathway or to the pilot overall | Recommended: per source pathway, coordinated at pilot level | Per source pathway
Q03 | Required | Defect severity threshold | State which defects must be corrected before go-live | Critical only; critical and high; all required-element defects | Critical and high
Q04 | Required | Post-go-live remediation | Confirm that priority defects may be corrected during early operations | Yes; no | Yes
Q05 | Required | Unresolved defects after cycle two | Select treatment | Document and accept limitation; remove source; separately fund; delay acceptance | Document and accept limitation or remove source
Q06 | Required | Participant replacement | State whether a failed provider may be replaced | Yes; no; only before go-live | Only before go-live
Q07 | Required | Go-live acceptance authority | Identify who makes the final go-live decision | Sponsor; STLT; intermediary; joint decision | STLT
Q08 | Required | Minimum go-live criteria | Define the minimum conditions for exchange to begin | Minimum cohort, core elements, primary output, security approval, operational support | Minimum cohort, core elements, primary output, security approval, operational support
O01 | Required | Service expectations | Identify whether formal service levels are required | Best effort; defined response targets; formal SLA | Formal SLA
O02 | Required | Support coverage | Define support hours during live operations | Business hours; extended hours; 24×7 | Business hours
O03 | Required | Operational reporting cadence | State how often intermediary performance reports are required | Weekly; monthly; quarterly | Monthly
O04 | Required | Secondary-use frequency | State how often the second-use artifact must be generated | Once; twice; monthly; quarterly | Quarterly
O05 | Required | Exchange-period success threshold | Define the minimum successful reporting-cycle completion rate | Example: 90%, 95%, or another threshold | 95%
O06 | Required | Source continuity requirement | State whether every provider must remain active for the full period | All sources; minimum cohort only; defined percentage | Minimum cohort
E01 | Required | Evaluation dimensions | Select the required evaluation domains | Data quality; conformance; timeliness; reliability; burden; utility; reuse; cost; sustainability | Data quality; conformance; timeliness; reliability; burden; utility; reuse; cost; sustainability
E02 | Required | Baseline requirement | State whether baseline data must be collected before go-live | Recommended: yes | Yes
E03 | Required | Burden measurement | Identify how participant burden should be measured | Time reporting; interviews; surveys; ticket counts; qualitative only | Interviews and surveys
E04 | Required | Decision-utility evidence | Define what counts as evidence that the STLT used the output | Documented review; meeting decision; investigation; program action; user attestation | Program action; documented review; user attestation
E05 | Required | Cost evaluation | State whether actual participant and sponsor costs must be collected during the pilot | Yes; sponsor only; total economic cost; no | Yes
E06 | Required | Outcome-evaluation boundary | Confirm that clinical or population outcome improvement is not required | Recommended: exclude from base pilot | Excluded
E07 | Required | Final evaluation timing | State whether evaluation and reporting may overlap with live operations | Required for a nine-month target; recommended generally | Yes
E08 | Preferred | Independent evaluator requirement | State whether evaluation must be organizationally independent | Yes; no; partially independent | Yes
C01 | Required | Portfolio-shared assets available at launch | Identify which common assets will exist before pilot mobilization | Charter, governance, legal, security, architecture, testing, evaluation, training, playbook templates | Charter, governance, architecture, testing, evaluation, playbook templates
C02 | Required | Pilot-specific adaptation responsibility | Identify who adapts portfolio assets for the pilot | Portfolio PMO; pilot PMO; intermediary; shared | Portfolio PMO
C03 | Required | Common PMO treatment | State whether a central portfolio PMO will operate in addition to pilot PMO | Yes; no | Yes
C04 | Required | Common technical services | State whether architecture, conformance, legal, security, and evaluation experts are centrally funded | Yes; no; selected services only | No
C05 | Required | Shared-cost allocation method | Confirm how central work will be reflected in each pilot’s pro forma | Actual use; equal share; central only; multiple views | Central only
X01 | Required | Optional extensions | Confirm all work excluded from the base pilot | Custom dashboards; additional domains; extra measures; payer data; TEFCA; referrals; CBOs; AI; new MPI/IAM; more than two endpoints | Custom dashboards; additional domains; extra measures; payer data; TEFCA; referrals; CBOs; AI; new MPI/IAM; more than two endpoints
X02 | Required | Optional-cost schedule | State whether Stage 4 should price excluded extensions separately | Yes; no; selected extensions only | Yes
X03 | Preferred | Extensions to price | Identify any optional items you want included in the pro forma as add-ons | List items | None provided, need to make educated assumptions based on research from STAGE 2
A01 | Required | Low/base/high scenarios | Confirm whether Stage 4 should create three cost scenarios | Recommended: yes | Yes
A02 | Required | Base-case posture | Select the intended base scenario | Six-month minimum; nine-month target; exceptionally ready nine-month case | Six-month minimum; nine-month target
A03 | Required | High-case treatment | State whether the high case may exceed $3 million or must reduce scope to remain within the ceiling | Allow overrun visibility; force scope reduction; show both | Show both
A04 | Required | Sponsor-cost presentation | Select the primary budget view | Direct pilot cost only; direct plus allocated shared cost; both | Direct plus allocated shared cost
A05 | Required | Economic-cost presentation | Select whether total economic cost should appear alongside sponsor cost | Yes; no; appendix only | Appendix only
A06 | Required | Labor-rate basis | Identify the rate source Stage 4 should use | Existing contract rates; federal schedules; market rates; blended placeholder rates | Market rates from STAGE 2 research
A07 | Preferred | Known labor rates | Attach or provide applicable rates, if available | Rate card or contract labor categories | None provided, need to make educated assumptions based on research from STAGE 2
A08 | Preferred | Known vendor or intermediary quotes | Attach any available pricing or preliminary estimates | Quote, budgetary estimate, or none | None provided, need to make educated assumptions based on research from STAGE 2