# Updated Assumptions

| Question | Why It Matters | Provisional Assumption |
| --- | --- | --- |
| How many intermediaries will participate, and of what types? | Largest driver of duplicated implementation and governance cost | Base case: 1 intermediary |
| How many STLT jurisdictions, provider networks, and individual facilities are expected? | Determines onboarding, interface, subaward, legal, and evaluation scale | Base: 1 STLTs, 6 provider networks |
| What is the definitive project duration and required live-operation period? | Drives PM, support, hosting, and evaluation | 12 months total; 4 months live operations |
| Which chronic domain and measures will be mandatory? | Determines data requirements, SME mix, licensing, and validation | One hypertension or diabetes domain; 1–2 measures |
| Is the optional referral extension part of the funded pilot? | Could add an independent workstream and new organization types | Exclude from base; model separately |
| Will a new shared pilot hub be built, or will each intermediary host all processing? | A central platform could be the largest fixed technical cost | Existing intermediary hosting in base case |
| What existing FHIR endpoints and source connections are actually available? | Determines whether the project is configuration or greenfield integration | At least 50% of source pathways already connected |
| Who will receive direct funding—STLTs, intermediaries, HCCNs, providers, vendors, CBOs? | Required to distinguish sponsor cost from total economic cost | Fund STLTs/intermediaries; track provider effort in kind |
| What data-access level will each consumer receive? | Changes privacy, security, de-identification, and architecture | STLTs may receive line-level; national uses primarily de-identified or aggregate |
| Are HRSA and NCQA formal pilot participants or advisory stakeholders? | Changes measure licensing, validation, deliverables, and governance | Advisory in base case |
| What security framework and approval process applies? | Security review can materially affect schedule and cost | Intermediary controls plus participant review; no CDC ATO assumed unless CDC-hosted |
| What are the required acceptance thresholds? | Necessary to determine testing and remediation scope | Defined during design; cap at two remediation cycles |